## README
Phase 1 — Discovery Validation & Augmentation
Purpose | Close gaps in Discovery outputs before Detailed Design accelerates. Time-boxed 4-6 weeks.
Context | Discovery was led by a senior front-end developer as tech lead. Outputs likely uneven: strong where the internal team compensated, weaker in systems-level, backend, integration, and data dimensions.
Led by | Chief Architect + designated Senior Engineer Deputy. Supported by: Product Council, vendor code-archaeology resource, BAs.
Tabs
1. Validation Checklist | 10-category checklist. Work through systematically. Each item marked Verified / Gap / Rework.
2. Gap Register | Every identified gap with severity, disposition, owner, close date. Single source of truth.
3. Artifact Inventory | Every Discovery artifact being validated, with reviewer and status.
4. Integration Augmentation | Per-integration deep-dive using the full 16-point specification.
5. State Machine Register | Workflow objects needing formal state machine specification.
6. Failure Mode Catalog | FMEA-style catalog of failure scenarios and current design adequacy.
7. Validation Workshops | Schedule, attendees, outputs for the validation workshops.
8. Vendor Code Archaeology | Business rule extraction batches, status, and completeness.
Discipline
Time-box | 4-6 weeks maximum. Extension requires executive approval.
Scope | Validate, don't redo. Do not re-open behavioral decisions Discovery made; do verify system-level grounding.
Parking | Gaps that need weeks of analysis get parked in Design backlog, not addressed in the validation window.
Acceptance | Chief Architect + Senior Eng deputy + Program Manager sign baseline for Design entry.
Entry criteria | Chief Architect onboarded, Senior Eng deputy designated, all Discovery artifacts gathered.
Exit criteria | Gap Register all items dispositioned; Augmented artifacts published; Baseline memo signed.

## 1. Validation Checklist
Validation Checklist — 10 Categories
Work through systematically. Mark each item Verified / Gap / Rework. Any Gap or Rework creates a row in Gap Register.
Do not soften assessments. Honest categorization now saves rework later.
# | Category | Checklist Item | Owner | Status | Gap ID (if any) | Notes
1 | Feature Catalog | Every feature has a clear owner (operator persona or system)
2 | Feature Catalog | Every feature has priority and MVP/non-MVP classification
3 | Feature Catalog | Taxonomy covers operational workflow, supervisory, reporting, admin, integration, observability, security/audit, training
4 | Feature Catalog | Cross-cutting capabilities represented (audit logging, notifications, search, export, batch operations)
5 | Feature Catalog | Scheduled maintenance features distinct from reactive features
6 | Feature Catalog | Steam, Di-Electric, RTU/Telephonic features distinct (not lumped into 'other')
7 | Feature Catalog | Features sized realistically — any 'feature' that is actually 30 sub-features flagged
8 | Functional Requirements | Each FR has at least one acceptance criterion or example
9 | Functional Requirements | FRs cover state transitions, not only actions
10 | Functional Requirements | Negative paths and failure cases represented
11 | Functional Requirements | Timing, ordering, and temporal constraints explicit
12 | Functional Requirements | Override and exception workflows captured
13 | Functional Requirements | Multi-user / concurrent scenarios addressed (two operators on same card, shift handoff, conflicting switching orders)
14 | Functional Requirements | System-internal behaviors (retry, reconciliation, cleanup) represented
15 | Business Rules | Rules documented from legacy functional specifications
16 | Business Rules | Rules embedded in legacy code identified for extraction (vendor task)
17 | Business Rules | Each rule has: condition, consequence, rationale, applicability scope
18 | Business Rules | State-dependent rules distinguished from static rules
19 | Business Rules | Safety-critical rules flagged explicitly; two-person validation trail documented
20 | Business Rules | Rules with known legacy exceptions / overrides documented
21 | Business Rules | Obsolete rules identified for deprecation consideration
22 | NFRs | Each NFR has a measurement method defined
23 | NFRs | Performance NFRs traced to expected workload profiles (normal, peak, storm)
24 | NFRs | Availability NFRs traced to redundancy and failover architecture
25 | NFRs | Scalability NFRs include capacity for 5-year growth projection
26 | NFRs | Security NFRs map to compliance framework controls (NERC CIP, state PUC)
27 | NFRs | Audit NFRs specify retention duration and retrieval performance
28 | NFRs | Recoverability NFRs include RPO/RTO per subsystem with documented rationale
29 | NFRs | Operability NFRs capture deployment, monitoring, on-call concerns
30 | NFRs | NFRs checked against known legacy system actual behavior (gaps vs. aspirations)
31 | NFRs | NFRs include testability statement — how each will be validated
32 | System Inventory | All integrated systems cataloged with name, vendor, ownership, protocol, criticality
33 | System Inventory | Each system's expected availability and impact on our system when unavailable
34 | System Inventory | Data volume and velocity at each integration boundary characterized
35 | System Inventory | Authentication mechanism per system
36 | System Inventory | Test environment availability per system
37 | System Inventory | Data classification sensitivity per integration
38 | System Inventory | Read-only vs. read-write boundaries explicit
39 | System Inventory | Known-quirky behaviors per system documented (vendor resource valuable here)
40 | System Inventory | Retirement roadmap per legacy system documented
41 | Integration Depth | Protocol + message format + schema documented
42 | Integration Depth | Synchronous vs. asynchronous explicit
43 | Integration Depth | Event ordering semantics characterized
44 | Integration Depth | Idempotency keys and deduplication approach specified
45 | Integration Depth | Retry semantics on both sides documented
46 | Integration Depth | Error response catalog complete
47 | Integration Depth | Volume profile: normal, peak, storm-day
48 | Integration Depth | Latency profile: P50, P95, P99 under each load
49 | Integration Depth | Failure modes: partial, duplicate, out-of-order, loss, corruption
50 | Integration Depth | Reconciliation approach for state drift documented
51 | Integration Depth | Monitoring and alerting specified
52 | Integration Depth | Contact/ownership documented including 3am response path
53 | Data Model | Entity list complete across all five domains
54 | Data Model | Relationships and cardinalities documented
55 | Data Model | Aggregate boundaries identified (consistency vs. eventual)
56 | Data Model | Ownership: which service/module owns which entity
57 | Data Model | Historical/temporal entities distinguished from state entities
58 | Data Model | Reference data vs. operational data separated
59 | Data Model | Data sensitivity classification per entity
60 | Data Model | Expected volume per entity (normal and 5-year projection)
61 | Data Model | Retention requirements per entity (regulatory and business)
62 | Data Model | Legacy data model anomalies documented
63 | State Machines | State machines explicit for Card, Switching Order, Switching Step, Clearance, other long-lived objects
64 | State Machines | Valid state transitions enumerated; invalid transitions identified
65 | State Machines | Precondition predicates per transition documented
66 | State Machines | Postcondition predicates per transition documented
67 | State Machines | Compensating actions for failed transitions defined
68 | State Machines | Timeout behavior per state defined
69 | State Machines | Concurrent access rules per state (contention, locking, conflict resolution)
70 | State Machines | Cross-object coordination rules documented
71 | Operational & Edge | Storm-day scenario modeled end-to-end (volume, concurrency, card load, dispatch queue)
72 | Operational & Edge | SCADA/EMS unavailable — degraded behavior defined
73 | Operational & Edge | Field work system unavailable — degraded behavior defined
74 | Operational & Edge | GIS/CIS unavailable — graceful degradation defined
75 | Operational & Edge | Network partition between datacenters — failover behavior defined
76 | Operational & Edge | Single operator working night shift — workload and escalation defined
77 | Operational & Edge | Shift handoff during active switching order — protocol defined
78 | Operational & Edge | Switching order abandonment mid-execution — reversal behavior defined
79 | Operational & Edge | Emergency bypass / override scenarios defined for critical safety rules
80 | Operational & Edge | Regulatory audit scenario — evidence retrieval walkthrough documented
81 | Domain Coverage | Distribution coverage equivalent across categories
82 | Domain Coverage | Transmission coverage equivalent across categories
83 | Domain Coverage | Di-Electric coverage equivalent across categories
84 | Domain Coverage | RTU/Telephonic coverage equivalent across categories
85 | Domain Coverage | Steam coverage equivalent across categories
SUMMARY
Total items: | 85
Verified: | 0
Gap: | 0
Rework: | 0
% Verified: | 0%

## 2. Gap Register
Gap Register
Every gap found during validation. Disposition must be explicit: close now / defer to design / defer to build / accept risk.
Severity: CRITICAL = block Design entry; HIGH = close early in Design; MEDIUM = address during Design; LOW = track only.
Gap ID | Category | Description | Why It Matters | Severity | Recommended Action | Effort (S/M/L) | Disposition | Owner | Target Close Date | Status
G-001 | Integration Depth | SCADA event ordering semantics not specified beyond 'events arrive in order' | System may be designed assuming exactly-once ordered delivery when SCADA can produce out-of-order events during recovery; silent correctness failures possible | CRITICAL | Integration Architect + SCADA team workshop; document ordering guarantees formally; update integration spec | M | Close Now | Integration Architect |  | Open
G-002 | NFRs | NFR-007 (step precondition accuracy = 100%) has no measurement method defined | 100% accuracy is untestable without explicit safety test suite; risk of claiming compliance without evidence | CRITICAL | Define safety test suite; historical switching order replay; formal verification approach | L | Close Now | Chief Architect |  | Open
G-003 | State Machines | Abandoned switching order reversal workflow not formalized | Implementation will be ad-hoc; safety-critical reversal logic at risk of defect; BR-SW-020 references but not specified | HIGH | Workshop with Product Council; formalize reversal state machine; derive test cases | M | Defer to Design | Chief Architect + Sr Eng Deputy |  | Open
G-004 | Data Model | Di-Electric fluid-pressure time-series storage and retention not addressed | Regulatory retention requirements unknown; may require time-series DB decision; affects architecture | HIGH | Engage Di-Electric SME; determine retention; ADR for time-series approach | M | Close Now | Data Architect |  | Open
G-005 | Operational & Edge | Shift handoff during active switching order — protocol undefined | Operator confusion during handoff could lead to duplicated or missed steps; safety implication | HIGH | Workshop with active shift supervisors; define handoff protocol; story in MVP | S | Close Now | Product Owner |  | Open
G-006 | Domain Coverage | Steam system coverage significantly shallower than Distribution across all categories | Steam modernization may be under-scoped; risk of late-phase scope discovery | MEDIUM | Dedicated Steam workshop; validate feature/rule completeness; adjust backlog | L | Defer to Design | BA + Steam SME |  | Open
G-007 | Business Rules | Rules embedded in legacy restoration priority algorithm not documented anywhere | Behavior invisible to anyone but the legacy code; feature parity risk | HIGH | Priority target for vendor code archaeology Batch 2 | M | Defer to Build | Vendor Resource + Data Architect |  | Open
G-008 | Functional Requirements | Concurrent card editing by two operators — behavior undefined | Race condition in implementation; operator experience inconsistent | MEDIUM | Define concurrency model; pessimistic vs. optimistic locking ADR | M | Defer to Design | Sr Eng Deputy |  | Open
G-009 | Integration Depth | Field Work System dispatch ack timeout — not specified | Orphan dispatch risk; outbox pattern specifics need ack semantics | HIGH | Field Work System vendor engagement; ack timeout specification | S | Close Now | Integration Architect |  | Open
G-010 | System Inventory | GIS retirement roadmap — current GIS being replaced by enterprise team in parallel | Our integration target may change mid-build; rework risk | HIGH | Engage GIS program; determine integration target; bridge strategy | M | Close Now | Program Manager + Integration Architect |  | Open
G-011 | NFRs | Operability NFRs (on-call MTTR, runbook coverage) not present | Operational readiness not measurable; hypercare exit criteria weak | MEDIUM | Add operability NFRs; re-signature round required | S | Defer to Design | DevOps Lead + Program Manager |  | Open
G-012 | Operational & Edge | Emergency bypass / override scenarios for grounding rules — undefined | Safety-critical rule (BR-SAFETY-003) says no override; validate this absolute rule against real operational scenarios | HIGH | Product Council deep-dive; confirm absolute rule vs. needing narrow escape hatch | S | Close Now | Product Council + Chief Architect |  | Open
SUMMARY
Total gaps: | -152
CRITICAL: | 2
HIGH: | 7
MEDIUM: | 3
LOW: | 0
Open: | 12
In Progress: | 0
Closed: | 0
Blocking Design entry (CRITICAL Open/In Progress): | 2

## 3. Artifact Inventory
Discovery Artifact Inventory
Every Discovery output being validated. One row per artifact. Reviewer sign-off indicates validation complete for that artifact.
Link column should point to the artifact location (wiki, SharePoint, Confluence, file path).
Artifact ID | Artifact Name | Type | Location/Link | Reviewer | Review Status | Review Date | Baseline Version | Notes
DA-001 | Feature Catalog — master | Catalog | wiki/discovery/features | Chief Architect + PO | In Review |  | v1.0
DA-002 | Functional Requirements Document | Requirements | wiki/discovery/fr | Sr Eng Deputy | In Review |  | v1.0
DA-003 | Business Rules Register (from spec) | Register | wiki/discovery/br | Chief Architect | In Review |  | v1.0 | Code-extracted rules merging in parallel via vendor work
DA-004 | NFR Catalog (signed) | Catalog | wiki/discovery/nfr | Chief Architect | Not Started |  | v1.0 | Signed — validate grounding
DA-005 | System Inventory | Inventory | wiki/discovery/systems | Integration Architect | Not Started |  | v1.0
DA-006 | Integration Map (high-level) | Map | wiki/discovery/integrations | Integration Architect | In Review |  | v1.0 | Will be decomposed into per-integration deep-dives
DA-007 | Data Entity Inventory (preliminary) | Inventory | wiki/discovery/data | Data Architect | Not Started |  | v1.0
DA-008 | Use Case / User Journey Document | Use Cases | wiki/discovery/usecases | Product Owner | In Review |  | v1.0
DA-009 | Personas and Role Model | Personas | wiki/discovery/personas | UX Designer | Verified |  | v1.0 | Strength of Discovery
DA-010 | UX Flows / Wireframes | Design | figma/project/discovery | UX Designer | Verified |  | v1.0 | Strength of Discovery
DA-011 | Glossary / Domain Terms | Glossary | wiki/discovery/glossary | BA Lead | In Review |  | v1.0
DA-012 | Stakeholder Map | Map | wiki/discovery/stakeholders | Program Manager | Verified |  | v1.0
DA-013 | Constraints & Assumptions Log | Log | wiki/discovery/constraints | Chief Architect | In Review |  | v1.0
DA-014 | Legacy System Capability Map | Map | wiki/discovery/legacy | Vendor Resource + Sr Eng | In Review |  | v1.0 | Feeds feature parity matrix

## 4. Integration Augmentation
Integration Augmentation Tracker
Per-integration deep-dive covering the full 16-point specification. Each column is an integration; rows are specification dimensions.
UNKNOWN entries are questions for the integration partner. Do not fabricate — flag explicitly.
Specification Dimension | SCADA/EMS | Field Work System | GIS | CIS | Enterprise Auth (SSO) | Asset Management
1. Protocol / format / schema | IEC 61850 / SCADA proprietary event format over Kafka
2. Interaction pattern (sync/async/batch/poll) | Async — event stream consumer
3. Ordering semantics | Per-device partition ordered; global unordered
4. Idempotency keys / dedup window | Event ID (UUID); 15-min dedup window
5. Volume — normal (events/sec) | 500/s
6. Volume — peak storm (events/sec) | 5,000/s (storm peak observed 2023)
7. Latency P50 / P95 / P99 | P50 < 100ms, P95 < 500ms, P99 < 2s (source)
8. Availability SLA | 99.95% per SCADA vendor SLA
9. Behavior when integration unavailable | Our system enters degraded mode; operators continue via UI; events queued on recovery
10. Authentication mechanism | mTLS + shared topic subscription credentials
11. Credential lifecycle / rotation | Cert rotation every 6 months; process defined
12. Error response catalog | See SCADA integration doc §5.3 — 14 error codes cataloged
13. Failure modes (partial/dup/reorder/loss) | Partial: possible; Duplicate: possible within 15 min; Reorder: possible on recovery; Loss: possible on extended outage > 2hr
14. Reconciliation approach | Daily reconciliation job compares SCADA device state to our last-known state
15. Security (TLS / at-rest / classification) | TLS 1.3 in transit; encrypted Kafka cluster at rest; data not customer-sensitive
16. Monitoring / alerts / runbook entry | Consumer lag, error rate, topic throughput dashboards; alert on lag > 5 min
17. Ownership / 3am contact | SCADA ops team 24/7; escalation to SCADA vendor L3 support
18. Test environment availability | Staging SCADA replica available; production-fidelity 80%
19. Known quirks / historical issues | Replay on recovery can exceed 30min and backfill events in unusual order
20. Retirement / roadmap | SCADA vendor major upgrade planned Y+3; maintain ACL pattern
21. Validation status | In Progress
22. Gap reference (G-###) | G-001, G-009 referenced

## 5. State Machine Register
State Machine Register
Long-lived workflow objects requiring formal state machine specification. Each object gets a dedicated workshop during the validation window.
Output of each workshop: transition table, precondition/postcondition predicates, concurrent-access rules, compensating actions.
SM ID | Workflow Object | Domain | Safety-Critical? | Workshop Date | Workshop Lead | Output Status | Transition Table Link | Gaps Referenced | Notes
SM-01 | Trouble Card | Cross-cutting | N |  | Sr Eng Deputy | Not Started |  |  | Multi-path: auto-created, manually-created, bulk-opened
SM-02 | Switching Order | Cross-cutting | Y |  | Chief Architect | Not Started |  |  | Most complex; highest safety concern
SM-03 | Switching Step (within Order) | Cross-cutting | Y |  | Chief Architect | Not Started |  |  | Preconditions/postconditions are here
SM-04 | Clearance | Cross-cutting | Y |  | Sr Eng Deputy | Not Started |  |  | Device-scope enforcement
SM-05 | Hold-Off (Hot-Line Tag) | Cross-cutting | Y |  | Sr Eng Deputy | Not Started
SM-06 | Dispatch (Field Work) | Cross-cutting | N |  | Integration Architect | Not Started |  |  | Crosses integration boundary
SM-07 | Incident / Outage | Cross-cutting | N |  | BA Lead | Not Started
SM-08 | Abnormal Configuration Record | Cross-cutting | N |  | BA Lead | Not Started |  | G-003
SM-09 | Planned Maintenance Request | Cross-cutting | N |  | BA Lead | Not Started |  |  | Post-MVP but formalize now
SM-10 | Di-Electric Pressure Event | Di-Electric | Y |  | Di-Electric SME + Sr Eng | Not Started |  | G-004 | Domain-specific lifecycle
SM-11 | Steam Operation | Steam | N |  | Steam SME + Sr Eng | Not Started |  | G-006

## 6. Failure Mode Catalog
Failure Mode & Degraded Operation Catalog
Systematic enumeration of failure scenarios with current design adequacy.
Severity × Likelihood × Detection-difficulty = Risk Priority Number (RPN). RPN >= 30 requires mitigation plan.
FM ID | Scenario | Failure Class | Likelihood (1-5) | Impact (1-5) | Detection Difficulty (1-5) | RPN | Current Design Adequacy | Mitigation Plan | Owner | Target Close | Status
FM-01 | SCADA/EMS becomes unavailable for > 30 minutes during storm | External | 3 | 5 | 1 | 15 | Needs Work | Define degraded mode behavior; event queueing strategy; operator UI indication | Integration Architect |  | Open
FM-02 | SCADA event backlog replay after extended outage (>2hr) | External | 3 | 4 | 2 | 24 | Not Addressed | Backpressure strategy; replay prioritization; rate limiting | Integration Architect |  | Open
FM-03 | Field Work System unavailable; dispatches cannot flow | External | 2 | 4 | 1 | 8 | Partial | Outbox with queued dispatches; manual dispatch bypass; operator visibility | Integration Architect |  | Open
FM-04 | Database primary failure during active switching order | Internal | 2 | 5 | 1 | 10 | Adequate | Patroni failover; connection pooling; transaction semantics | Infrastructure Architect |  | Open
FM-05 | Full datacenter failure (DR scenario) | Internal | 1 | 5 | 1 | 5 | Adequate (tested) | DR site activation playbook; RPO/RTO validated | Infrastructure Architect |  | Open
FM-06 | Partial DB degradation — slow queries saturate connections | Internal | 3 | 4 | 3 | 36 | Not Addressed | Connection pool sizing; query timeout; circuit breaker | DBA + Sr Eng |  | Open
FM-07 | Network partition between datacenters | Internal | 2 | 4 | 2 | 16 | Partial | Split-brain prevention; witness arbitration | Infrastructure Architect |  | Open
FM-08 | Kafka broker loss during peak ingestion | Internal | 2 | 4 | 2 | 16 | Partial | 3+ broker cluster with replication factor 3; producer retry | Platform Tech Lead |  | Open
FM-09 | Storm + SCADA high volume + DB degradation (cascading) | Cascading | 2 | 5 | 4 | 40 | Not Addressed | End-to-end backpressure; shedding strategy; degraded UI mode | Chief Architect |  | Open
FM-10 | Shift handoff during active switching order execution | Operational | 4 | 3 | 2 | 24 | Not Addressed | Handoff protocol definition; explicit acknowledgment step | Product Owner + Sr Eng |  | Open
FM-11 | Switching order abandonment mid-execution | Operational | 3 | 4 | 2 | 24 | Partial | Reverse-steps state machine (SM-02, SM-03); BR-SW-020 | Chief Architect |  | Open
FM-12 | Database failover while switching order in mid-execution | Cascading | 1 | 5 | 2 | 10 | Partial | Transaction boundaries; state recovery; operator resume workflow | Chief Architect |  | Open
FM-13 | Silent corruption — SCADA state diverges from our state | External | 2 | 5 | 5 | 50 | Not Addressed | Daily reconciliation; divergence alerting; operator override | Integration Architect |  | Open
FM-14 | Auth / SSO provider unavailable | External | 2 | 4 | 1 | 8 | Partial | Cached credentials window; emergency access procedure | Security Architect |  | Open
FM-15 | Storm load causes UI response time degradation > 10x | Cascading | 3 | 3 | 1 | 9 | Partial | Client-side caching; server-side degradation; feature throttling | Frontend Tech Lead |  | Open
SUMMARY
Total failure modes: | -152
High RPN (>=50): | 1
Medium RPN (30-49): | 2
Not Addressed: | 5
Needs Work: | 1
Adequate or better: | 2

## 7. Validation Workshops
Validation Workshops Log
Schedule of validation workshops during the 4-6 week window. Each workshop produces specific outputs captured in the relevant tabs.
Post-workshop: decisions and gaps logged in Gap Register; outputs filed in appropriate augmentation tabs.
Workshop ID | Topic | Date Planned | Date Held | Duration | Lead | Attendees | Outputs / Notes
WS-01 | SCADA/EMS Integration Deep-Dive | Week 1 |  | Half-day | Integration Architect | Chief Architect, Sr Eng, SCADA team liaison, vendor resource
WS-02 | Field Work System Integration Deep-Dive | Week 1 |  | Half-day | Integration Architect | Chief Architect, Sr Eng, Field Work vendor liaison
WS-03 | GIS Integration Deep-Dive | Week 2 |  | Half-day | Integration Architect | Chief Architect, Sr Eng, GIS team liaison
WS-04 | CIS Integration Deep-Dive | Week 2 |  | Half-day | Integration Architect | Chief Architect, Sr Eng, CIS team liaison
WS-05 | Data Model Review (cross-domain) | Week 2 |  | Full-day | Data Architect | Chief Architect, Sr Engs, DBA, BAs, vendor resource
WS-06 | State Machine Formalization — Trouble Card | Week 3 |  | Half-day | Sr Eng Deputy | Chief Architect, Product Council operator, BA
WS-07 | State Machine Formalization — Switching Order | Week 3 |  | Full-day | Chief Architect | Sr Engs, Product Council, BA, vendor resource | Most complex - extra time
WS-08 | State Machine Formalization — Switching Step | Week 3 |  | Full-day | Chief Architect | Sr Engs, Product Council, BA, vendor resource | Safety-critical preconditions/postconditions
WS-09 | State Machine Formalization — Clearance | Week 4 |  | Half-day | Sr Eng Deputy | Chief Architect, Product Council, BA
WS-10 | Failure Mode Analysis — External Dependencies | Week 4 |  | Full-day | Chief Architect | All Sr Engs, Integration Architect, Infrastructure Lead, Product Council
WS-11 | Storm-Day Scenario Modeling | Week 4 |  | Full-day | Chief Architect | All Sr Engs, Product Council, active shift supervisor liaison
WS-12 | NFR Grounding Review | Week 5 |  | Half-day | Chief Architect | Infrastructure Architect, Security Architect, QA Lead
WS-13 | Di-Electric / RTU / Steam Domain Coverage Check | Week 5 |  | Full-day | BA Lead | Domain SMEs, Sr Engs, Chief Architect
WS-14 | Business Rule Batch Review (recurring — weekly) | Weeks 2-6 |  | 2-hour | Data Architect | Vendor resource, Sr Eng, Product Council, BA | Recurring weekly during vendor extraction
WS-15 | Gap Register Review & Disposition | Week 5 |  | Half-day | Program Manager | Chief Architect, Sr Eng Deputy, Product Owners | Disposition every open gap
WS-16 | Baseline Acceptance Review | Week 6 |  | Half-day | Program Manager | Chief Architect, Sr Eng Deputy, Steering Committee rep | Signs baseline for Design entry

## 8. Code Archaeology
Vendor Code Archaeology Tracker
Business rule extraction from legacy code by vendor resource. Organized in batches by module/subsystem.
Each batch: scope, estimated rule count, actual rule count, test case count, Product Council validation status.
Batch ID | Module/Subsystem | Legacy Code Scope | Estimated Rules | Actual Rules Extracted | Tests Derived | Validation Status | Start Date | Complete Date | Notes
B-01 | SCADA Event Handler | legacy/oms/events/ | 12 | 0 | 0 | Not Started |  |  | Priority 1 - feeds MVP
B-02 | Trouble Card Core | legacy/oms/card/ | 18 | 0 | 0 | Not Started |  |  | Priority 1 - feeds MVP
B-03 | Switching Order Authoring | legacy/swman/author/ | 15 | 0 | 0 | Not Started |  |  | Priority 1 - safety-critical
B-04 | Switching Step Execution | legacy/swman/exec/ | 22 | 0 | 0 | Not Started |  |  | Priority 1 - safety-critical; highest volume
B-05 | Clearance / Tag Management | legacy/clr/ | 14 | 0 | 0 | Not Started |  |  | Priority 1 - safety-critical
B-06 | Customer Impact Calculation | legacy/oms/card/cust_* | 8 | 0 | 0 | Not Started |  |  | Priority 2
B-07 | Restoration Priority Algorithm | legacy/oms/rest/ | 10 | 0 | 0 | Not Started |  |  | Priority 2 — G-007 referenced
B-08 | Distribution Feeder Model | legacy/assets/dist/ | 12 | 0 | 0 | Not Started |  |  | Priority 2
B-09 | Transmission Feeder Model | legacy/assets/trans/ | 10 | 0 | 0 | Not Started |  |  | Priority 3 — NERC CIP
B-10 | Di-Electric Subsystem | legacy/dielectric/ | 15 | 0 | 0 | Not Started |  |  | Priority 3 — domain-specific
B-11 | RTU / Telephonic Line | legacy/rtu/ | 8 | 0 | 0 | Not Started |  |  | Priority 3
B-12 | Steam Subsystem | legacy/steam/ | 10 | 0 | 0 | Not Started |  |  | Priority 3
B-13 | Scheduled Maintenance | legacy/sched_maint/ | 12 | 0 | 0 | Not Started |  |  | Priority 3 — post-MVP
B-14 | Reporting / SAIDI/SAIFI | legacy/reporting/ | 8 | 0 | 0 | Not Started |  |  | Priority 3
|  | TOTALS | 174 | 0 | 0