## README
Phase 2 — Detailed Design
Purpose | Translate validated Discovery outputs into the architectural, data, integration, and epic-level decomposition needed for Build.
Duration | ~6 months. Runs in parallel with platform foundation provisioning.
Entry criteria | Phase 1 Baseline Acceptance Memo signed. All CRITICAL gaps closed. Chief Architect in role. Senior Engineer Deputy designated.
Exit criteria | All MVP-scope ADRs accepted. MVP Epic set decomposed to initial story level. Design Authority Board approves Build commencement. Platform foundation operational.
Tabs
1. ADR Log | Every architecture decision with status, alternatives, consequences, and dual signatures.
2. Epic Register | Feature-rollup Epics with MVP flag, priority, owner, sprint/quarter targeting, story count.
3. Architecture Diagrams | C4 diagram register: context, container, component, code-level. Version and publication location.
4. Technical Spikes | Time-boxed investigations for unknowns. Spike ID, question, duration, outcome.
5. Technology Selection | Stack decisions with evaluation criteria and rationale.
6. Design Reviews | Each DAB session: date, topic, participants, decisions, action items.
7. Cross-Cutting Matrix | Audit / observability / security / resilience design per component.
8. Integration Contracts | Per-integration contract version, schema, owner, signed-off.
9. Data Migration Plan | Per-entity migration approach, volume, dress-rehearsal targets.
10. NERC CIP Register | Component-by-component CIP applicability determination.
11. Design Risks | Phase 2-specific risks tracked separately from program risks.
Discipline
Dual signature | Every ADR signed by Chief Architect + Senior Engineer Deputy. This is the explicit countermeasure against legacy-pattern drift.
Design Authority Board (DAB) | Weekly standing meeting. All significant ADRs go through DAB. External architect review at 3-month mark.
Safety-critical gating | Safety-critical design requires Product Council sign-off in addition to technical signatures.
Legacy pattern vigilance | P2-05 (Legacy Pattern Detection) run against every major design artifact. Findings flagged even when uncomfortable.
Spike discipline | Spikes are time-boxed. If a spike exceeds budget, it is halted and the learning is captured as-is.

## 1. ADR Log
Architecture Decision Record Log
Every architectural decision recorded. Dual signature required: Chief Architect + Senior Engineer Deputy. Safety-critical decisions also require Product Council.
Status flow: Proposed → Under Review → Accepted → Superseded / Deprecated.
ADR ID | Title | Category | Status | Date Proposed | Date Accepted | Chief Architect Sig | Sr Eng Deputy Sig | Safety-Critical? | Product Council Sig | Superseded By | Summary | Link
ADR-001 | Primary programming language and framework: Java 21 + Spring Boot 3 | Platform | Accepted | 2026-01-15 | 2026-01-29 | CK | RS | N |  |  | Team fluency; Spring ecosystem maturity; long-term support; NERC CIP-friendly tooling | wiki/adr/001
ADR-002 | Primary data store: PostgreSQL 16 with Patroni HA | Platform | Accepted | 2026-01-15 | 2026-01-29 | CK | RS | N |  |  | Open-source; mature HA; team experience; PITR; strong on-prem support | wiki/adr/002
ADR-003 | Messaging: Apache Kafka for event streaming | Platform | Accepted | 2026-01-22 | 2026-02-05 | CK | RS | N |  |  | Storm-day durability; SCADA event backbone; replay; team skills | wiki/adr/003
ADR-004 | Distributed cache: Redis for session and read-cache | Platform | Accepted | 2026-01-22 | 2026-02-05 | CK | RS | N |  |  | Low-latency UI; standard operational pattern | wiki/adr/004
ADR-005 | Deployment pattern: VM-based with Ansible orchestration (no containers) | Deployment | Accepted | 2026-01-29 | 2026-02-12 | CK | RS | N |  |  | Organization constraint; NERC CIP boundary clarity; team Ansible expertise | wiki/adr/005
ADR-006 | Integration pattern for downstream systems: Transactional Outbox | Integration | Accepted | 2026-02-05 | 2026-02-19 | CK | RS | Y | BD |  | Eliminates dual-write consistency risk; idempotent retry; at-least-once semantics with dedup | wiki/adr/006
ADR-007 | Audit architecture: Event-sourced audit log with immutable append-only store | Security | Accepted | 2026-02-05 | 2026-02-19 | CK | RS | Y | BD |  | NERC CIP 7-year retention; tamper-evident; complete lineage; independent of operational store | wiki/adr/007
ADR-008 | Read model for reporting: CQRS with materialized views on replica | Data | Accepted | 2026-02-12 | 2026-02-26 | CK | RS | N |  |  | Reporting isolation from operational load; storm-day resilience for operators | wiki/adr/008
ADR-009 | Enterprise Authentication: SAML 2.0 SSO + MFA via enterprise IdP | Security | Accepted | 2026-02-12 | 2026-02-26 | CK | RS | N |  |  | Enterprise standard; CIP-compliant; centralized account lifecycle | wiki/adr/009
ADR-010 | Authorization model: Role-Based with attribute policies for district scope | Security | Accepted | 2026-02-19 | 2026-03-05 | CK | RS | Y | BD |  | District scope critical; override logging requires first-class auth context | wiki/adr/010
ADR-011 | Secrets management: HashiCorp Vault | Platform | Accepted | 2026-02-19 | 2026-03-05 | CK | RS | N |  |  | On-prem; NERC CIP-friendly; integrates with Ansible pipeline | wiki/adr/011
ADR-012 | Observability stack: Prometheus + Grafana + ELK + Jaeger | Platform | Accepted | 2026-02-26 | 2026-03-12 | CK | RS | N |  |  | Open-source; on-prem; team fluency; integrates across stack | wiki/adr/012
ADR-013 | Service decomposition: Modular monolith with strategic service separation | Architecture | Accepted | 2026-02-26 | 2026-03-12 | CK | RS | N |  |  | Operational simplicity for on-call; strategic services: SCADA ingestion, integration gateway, reporting, batch | wiki/adr/013
ADR-014 | Frontend framework: React with TypeScript; no SSR | Platform | Accepted | 2026-03-05 | 2026-03-19 | CK | RS | N |  |  | Team skills; component ecosystem; operator UI richness; no SEO requirement | wiki/adr/014
ADR-015 | API style: REST with OpenAPI contracts; gRPC for internal high-volume paths | Integration | Accepted | 2026-03-05 | 2026-03-19 | CK | RS | N |  |  | REST for broad integration compatibility; gRPC for SCADA ingestion performance | wiki/adr/015
ADR-016 | Schema migration tooling: Flyway with forward-only migrations | Data | Accepted | 2026-03-12 | 2026-03-26 | CK | RS | N |  |  | Simpler operational model; reversals via compensating migrations; audit trail | wiki/adr/016
ADR-017 | Switching Step state machine: Explicit state machine library | Safety | Under Review | 2026-03-19 |  |  |  | Y |  |  | Formal state machine reduces safety-critical logic defect surface; see SM-03 formalization | wiki/adr/017
ADR-018 | Reporting replica isolation: Separate physical PostgreSQL replica for reporting workload | Data | Under Review | 2026-03-26 |  |  |  | N |  |  | Prevents reporting queries from impacting operational SLOs during storm | wiki/adr/018
ADR-019 | Data migration approach: Phased with per-district cutover | Migration | Proposed | 2026-04-02 |  |  |  | N |  |  | Risk reduction; operator change absorption; parallel-run per district | wiki/adr/019
ADR-020 | NERC CIP boundary: Transmission subsystem in dedicated ESP with EAP | Compliance | Proposed | 2026-04-02 |  |  |  | Y |  |  | Isolates CIP Medium Impact from Distribution; audit evidence simpler; EAP enforced on integration | wiki/adr/020
ADR-021 | Disaster Recovery posture: Warm standby with synchronous replication to DR | Platform | Proposed | 2026-04-09 |  |  |  | N |  |  | RPO <=5min; RTO <=30min; automated failover per NFR-010/011 | wiki/adr/021
ADR-022 | Feature flag strategy: Trunk-based with flags for runtime control | Platform | Proposed | 2026-04-09 |  |  |  | N |  |  | Enables per-district phased cutover; safe rollout for large changes | wiki/adr/022
SUMMARY
Total ADRs: | -138
Accepted: | 16
Under Review: | 2
Proposed: | 4
Safety-Critical: | 5
Safety-Critical Accepted: | 3

## 2. Epic Register
Epic Register
Business-capability-aligned Epics targeted to program quarters. Updated from Phase 1 with sprint/quarter targeting.
MVP Epics complete by Month 16. Non-MVP Epics span through Month 34.
Epic ID | Name | Description | Business Outcome | Owner | Priority | MVP? | Target Quarter | Features Count | Stories Count | Story Points Total | Status | % Complete | Notes
E-OPS-01 | SCADA/EMS Event Ingestion | Real-time ingestion with dedup and correlation | SCADA events captured at storm volumes, no data loss | Operations PO | Must | Y | Q3Y1 | 8 | 14 | 87 | In Design |  | Critical path; ADR-015 gRPC
E-OPS-02 | Trouble Card Lifecycle | Auto-creation to closure with state machine | Every incident tracked and auditable | Operations PO | Must | Y | Q3Y1 | 12 | 18 | 102 | In Design
E-OPS-03 | Switching Order Authoring | Template-based authoring with validation | Operators author safe, validated orders efficiently | Operations PO | Must | Y | Q4Y1 | 9 | 15 | 78 | In Design
E-OPS-04 | Switching Order Execution | Stepwise execution with pre/post-condition validation | Unsafe preconditions block progress; safe execution tracked | Operations PO | Must | Y | Q1Y2 | 6 | 22 | 145 | In Design |  | Highest safety concern; ADR-017
E-OPS-05 | Clearance & Tag Management | Electronic issuance with device-scope enforcement | Work authorization traceable and safe | Operations PO | Must | Y | Q1Y2 | 7 | 12 | 68 | In Design
E-OPS-06 | Restoration Tracking | Incident-to-normal with cause codes | Complete restoration records for ops and regulatory | Operations PO | Must | Y | Q2Y2 | 5 | 9 | 45 | Design
E-OPS-07 | District Operator Dashboard | Real-time situational awareness | Single pane of glass for operators | UX Lead + Ops PO | Must | Y | Q4Y1 | 8 | 16 | 89 | In Design |  | UX critical
E-OPS-08 | Operator Handoff | Structured handoff with acknowledgment | Shift transitions preserve context | Operations PO | Should | N | Q3Y2 | 3 | 7 | 32 | Backlog
E-OPS-09 | Abnormal Config Tracking | Track when network off-normal | Visibility of in-progress work state | Operations PO | Must | Y | Q2Y2 | 4 | 8 | 42 | Backlog
E-OPS-10 | Scheduled Maintenance Planning | Plan, approve, schedule planned outages | Planned work coordinated without conflicts | Operations PO | Should | N | Q4Y2 | 10 | 14 | 76 | Backlog |  | Post-MVP
E-AST-01 | Distribution Feeder Management | Feeder topology and devices | Distribution model supports all switching | Asset Mgmt PO | Must | Y | Q3Y1 | 8 | 10 | 54 | In Design
E-AST-02 | Transmission Feeder Management | Transmission with protection scheme awareness | Transmission supported; CIP-compliant | Asset Mgmt PO | Must | N | Q2Y2 | 10 | 14 | 82 | Design |  | ADR-020 CIP boundary
E-AST-03 | Di-Electric System Management | Fluid systems with domain rules | Di-Electric operations safe and compliant | Asset Mgmt PO | Must | N | Q3Y2 | 6 | 11 | 58 | Backlog
E-AST-04 | RTU & Telephonic Line Mgmt | SCADA comms infrastructure as assets | SCADA blind spots visible | Asset Mgmt PO | Should | N | Q4Y2 | 4 | 8 | 38 | Backlog
E-AST-05 | Steam System Management | Steam mains, valves, pressure zones | Steam ops in switching model | Asset Mgmt PO | Should | N | Q1Y3 | 8 | 13 | 71 | Backlog
E-INT-01 | SCADA/EMS Integration | Event consumption + state queries | Reliable storm-volume integration | Integration Lead | Must | Y | Q3Y1 | 5 | 10 | 68 | In Design |  | Critical path
E-INT-02 | Field Work System Integration | Dispatch and status reconciliation | Seamless dispatch and tracking | Integration Lead | Must | Y | Q4Y1 | 4 | 9 | 54 | In Design
E-INT-03 | GIS Integration | Topology sync | Current network topology reflected | Integration Lead | Must | Y | Q4Y1 | 3 | 6 | 38 | Design
E-INT-04 | CIS Integration | Customer lookup and impact calc | Customer impact on cards accurate | Integration Lead | Must | Y | Q1Y2 | 3 | 6 | 34 | Design
E-INT-05 | AMI Integration (outage confirmation) | Smart meter outage signal ingestion | Card accuracy improved via AMI | Integration Lead | Could | N | Q2Y3 | 2 | 4 | 24 | Backlog |  | Post-parity enhancement
E-PLT-01 | Authentication & Authorization | SSO, RBAC, district scope | Secure, auditable access control | Security PO | Must | Y | Q3Y1 | 4 | 8 | 48 | In Design |  | ADR-009/010
E-PLT-02 | Audit & Event Sourcing | Immutable audit log | Complete regulatory audit trail | Security PO | Must | Y | Q3Y1 | 3 | 8 | 48 | In Design |  | ADR-007
E-PLT-03 | Observability Platform | Metrics, logs, traces, alerts | Operational visibility for on-call | Platform PO | Must | Y | Q3Y1 | 6 | 12 | 62 | In Design |  | ADR-012
E-PLT-04 | Reporting & Dashboards | Regulatory and operational reporting | SAIDI/SAIFI and operational KPIs | Ops Reporting PO | Must | N | Q2Y2 | 8 | 15 | 84 | Backlog
E-PLT-05 | Data Migration | Legacy data migration to new schema | Historical data preserved and queryable | Data Migration Lead | Must | Y | Q3Y2 | 7 | 18 | 112 | Design |  | Per-district phased
E-PLT-06 | Training & Simulation | Training environment and scenarios | Operators trained prior to cutover | OCM Lead | Must | Y | Q2Y3 | 5 | 10 | 58 | Backlog
SUMMARY
Total Epics: | -132
MVP Epics: | 18
In Design: | 17
Total Story Points: | 1697
MVP Story Points: | 1232

## 3. Architecture Diagrams
Architecture Diagram Register
C4 model diagrams: Context / Container / Component / Code. Every major diagram registered with version and link.
Diagrams updated when corresponding ADRs change. Single source of truth in wiki/architecture/diagrams.
Diagram ID | Name | C4 Level | Scope / Area | Version | Status | Owner | Last Updated | Location / Link
DG-001 | System Context Diagram | Context | Whole system | 1.0 | Published | Chief Architect | 2026-02-15 | wiki/arch/c4-context
DG-002 | Container Diagram | Container | Whole system | 0.8 | In Review | Chief Architect | 2026-03-20 | wiki/arch/c4-container
DG-003 | Component Diagram - SCADA Ingestion Service | Component | SCADA ingestion service | 0.7 | In Review | Integration Architect | 2026-03-25 | wiki/arch/comp/scada
DG-004 | Component Diagram - Trouble Card Module | Component | Card module (in monolith) | 0.5 | Draft | Sr Eng Deputy | 2026-03-28 | wiki/arch/comp/card
DG-005 | Component Diagram - Switching Order Module | Component | Switching order + step modules | 0.3 | Draft | Chief Architect | 2026-04-01 | wiki/arch/comp/sword
DG-006 | Component Diagram - Clearance Module | Component | Clearance module | 0.2 | Draft | Sr Eng | 2026-04-02 | wiki/arch/comp/clr
DG-007 | Component Diagram - Integration Gateway | Component | Integration gateway service | 0.5 | Draft | Integration Architect | 2026-04-03 | wiki/arch/comp/intgw
DG-008 | Component Diagram - Audit Service | Component | Event-sourced audit log | 0.3 | Draft | Security Architect | 2026-04-04 | wiki/arch/comp/audit
DG-009 | Deployment Diagram - Production | Deployment | Prod VMs and networking | 0.6 | In Review | Infrastructure Architect | 2026-03-22 | wiki/arch/deployment/prod
DG-010 | Deployment Diagram - DR Site | Deployment | DR site VMs and replication | 0.4 | Draft | Infrastructure Architect | 2026-03-22 | wiki/arch/deployment/dr
DG-011 | Data Flow - SCADA Event to Card | Flow | End-to-end card creation flow | 0.8 | In Review | Sr Eng Deputy | 2026-03-18 | wiki/arch/flows/scada-card
DG-012 | Data Flow - Switching Order Execution | Flow | End-to-end step execution flow | 0.5 | Draft | Chief Architect | 2026-04-01 | wiki/arch/flows/sword-exec
DG-013 | State Diagram - Switching Order | State | Switching order state machine (SM-02) | 0.9 | In Review | Chief Architect | 2026-03-30 | wiki/arch/state/sword
DG-014 | State Diagram - Switching Step | State | Switching step state machine (SM-03) | 0.9 | In Review | Chief Architect | 2026-03-30 | wiki/arch/state/swstep
DG-015 | ERD - Core Data Model | Data | Core entities across domains | 0.5 | Draft | Data Architect | 2026-04-03 | wiki/arch/data/erd-core
DG-016 | Network Topology Diagram | Network | VLANs, ESPs, EAPs, firewalls | 0.5 | Draft | Security Architect | 2026-03-28 | wiki/arch/net/topology

## 4. Technical Spikes
Technical Spike Tracker
Time-boxed investigations to resolve design unknowns. Spike must produce a specific decision or learning. When budget exceeded, spike halts — learning captured as-is.
Spike outputs feed ADRs, integration contracts, or data model decisions. Spikes are NOT for prototyping features.
Spike ID | Question | Budget (days) | Actual (days) | Started | Completed | Owner | Outcome | Decision / Learning | Downstream Artifact
SP-01 | Can Kafka sustain 5,000 events/sec with 3-broker cluster on our hardware? | 3 | 3 | 2026-02-03 | 2026-02-06 | Sr Eng A | Confirmed | Yes with partition count >=6 and tuned producer config; tested to 6,500 e/s | ADR-003 ratified
SP-02 | PostgreSQL Patroni failover duration under SCADA ingestion load | 2 | 2 | 2026-02-10 | 2026-02-12 | DBA + Sr Eng | Confirmed | Failover < 25s under load; acceptable for RTO | ADR-002 ratified
SP-03 | SCADA vendor stream API options: native vs. proxy? | 4 | 5 | 2026-02-17 | 2026-02-23 | Integration Architect | Decision | Native stream available; proxy adds 200ms latency and no benefit | Integration contract INT-01
SP-04 | CQRS implementation: synchronous projection vs. async via Kafka? | 3 | 3 | 2026-02-24 | 2026-02-27 | Sr Eng Deputy | Decision | Async via Kafka; projection lag < 1s acceptable for reporting | ADR-008
SP-05 | Can we use legacy device-model export for initial data migration seed? | 2 | 3 | 2026-03-02 | 2026-03-06 | Data Engineer | Partial | Yes for 80% of devices; edge cases need manual mapping | Migration plan E-PLT-05
SP-06 | State machine library evaluation: Spring Statemachine vs. custom | 3 | 4 | 2026-03-09 | 2026-03-13 | Sr Eng Deputy | Decision | Custom lightweight — Spring Statemachine overhead not justified; traceability easier with custom | ADR-017 (draft)
SP-07 | Can existing enterprise SSO IdP support our session requirements? | 2 | 2 | 2026-03-16 | 2026-03-18 | Security Architect | Confirmed | Yes with current configuration; MFA enforced for privileged roles | ADR-009
SP-08 | Field Work API: does it support idempotent dispatch? | 2 | 3 | 2026-03-23 | 2026-03-26 | Integration Architect | Partial | Idempotency on create; update semantics ambiguous - need vendor clarification | Integration contract INT-02 + vendor ticket
SP-09 | Switching step precondition library: data-driven vs. code-driven? | 5 | 0 |  |  | Chief Architect | Not Started |  | ADR-017
SP-10 | Outbox pattern implementation: library vs. custom? | 3 | 0 |  |  | Sr Eng A | Not Started |  | ADR-006 implementation detail
SP-11 | Report replica lag under storm-day write volume | 3 | 0 |  |  | DBA | Not Started |  | ADR-018
SP-12 | Feature flag framework evaluation (LaunchDarkly OSS vs. Unleash vs. custom) | 3 | 0 |  |  | Platform Tech Lead | Not Started |  | ADR-022
SP-13 | Switching step post-condition verification via SCADA: acceptable latency? | 4 | 0 |  |  | Integration Architect | Not Started |  | Informs story US-OPS-04-002
SP-14 | CIS API performance under storm-day lookup volume | 2 | 0 |  |  | Integration Architect | Not Started |  | INT-04 capacity planning
SP-15 | Legacy audit log migration: event-sourced replay feasibility? | 5 | 0 |  |  | Data Architect | Not Started |  | Migration E-PLT-05 scope decision

## 5. Technology Selection
Technology Selection Log
Stack decisions with candidates evaluated, selection rationale, and risk notes.
Every entry here should correspond to an ADR. Candidates rejected for weak reasons should be challenged via P2-04 Architecture Challenger.
Tech ID | Category | Selection | Version | Candidates Considered | Selection Rationale | Primary Risk | License/Cost Model | Related ADR | Notes
T-001 | Language/Runtime | Java 21 LTS | 21 | Java, Kotlin, C#/.NET, Go | Team fluency; LTS stability; Spring ecosystem; NERC CIP-friendly tooling | Talent market softening for Java; mitigation via training | Open-source (OpenJDK) | ADR-001
T-002 | Application Framework | Spring Boot 3 | 3.2+ | Spring Boot, Quarkus, Micronaut, plain Java | Team expertise; ecosystem maturity; long-term backing; fits non-containerized deployment | Spring version upgrade discipline required | Apache 2.0 OSS | ADR-001
T-003 | Primary Database | PostgreSQL | 16 | PostgreSQL, Oracle, SQL Server, DB2 | Open-source; mature HA; team experience; PITR; on-prem strong; cost | No enterprise support default; Crunchy/EDB option if needed | PostgreSQL License | ADR-002
T-004 | Database HA | Patroni + etcd | 3.2+ | Patroni, repmgr, pg_auto_failover, Oracle RAC | Proven Patroni operational model; etcd available from observability stack | etcd operational complexity | Apache 2.0 | ADR-002
T-005 | Message Broker | Apache Kafka | 3.7+ | Kafka, Pulsar, RabbitMQ, ActiveMQ | Event streaming fit; storm durability; replay; team skills | Storage growth management; quota discipline | Apache 2.0 | ADR-003
T-006 | Distributed Cache | Redis | 7+ | Redis, Memcached, Hazelcast, in-memory JVM | Low-latency; session store; rate limiting; broad ecosystem | RedisLabs license changes; OSS Redis fork trajectory | Open-source (Redis OSS) | ADR-004
T-007 | Reverse Proxy / Load Balancer | nginx | 1.26+ | nginx, HAProxy, Apache Traffic Server | Team familiarity; TLS termination; rate limiting; on-prem friendly | nginx commercial features not needed | BSD-like | - | Part of platform baseline
T-008 | Configuration Management / Deployment | Ansible | 9+ | Ansible, Puppet, Chef, Salt | Team skills; agentless; fits VM pattern; NERC CIP audit-friendly | Inventory discipline at scale | GPL (but no redistribution) | ADR-005
T-009 | Secrets Management | HashiCorp Vault | 1.15+ | Vault, CyberArk, enterprise KMS | On-prem; NERC CIP-friendly; broad integration; team skills | HA operational complexity | MPL-2.0 (BSL post-v1.14 not used) | ADR-011 | Pin to MPL version
T-010 | Metrics | Prometheus | 2.50+ | Prometheus, DataDog, Dynatrace, New Relic | Open-source; on-prem; pull-based fit; team skills | Storage scaling for long retention | Apache 2.0 | ADR-012
T-011 | Visualization | Grafana | 10+ | Grafana, Kibana, DataDog, vendor-specific | Open-source; multi-source; team skills | Dashboard sprawl without governance | AGPL-3.0 | ADR-012
T-012 | Log Aggregation | Elastic Stack (ELK) | 8+ | ELK, Loki, Splunk, Graylog | On-prem; mature; team skills; NERC CIP evidence retention | License model changes post-7.10; using OSS distro | Elastic License 2.0 / AGPL | ADR-012 | OpenSearch option
T-013 | Tracing | Jaeger | 1.55+ | Jaeger, Zipkin, Tempo | Open-source; OTEL-native; team skills | Storage backend selection for retention | Apache 2.0 | ADR-012
T-014 | API Gateway | Spring Cloud Gateway | 4+ | Spring Cloud Gateway, Kong, Tyk, HAProxy | In-stack with rest of platform; team skills | Alternative would give more features but add operational surface | Apache 2.0 | -
T-015 | Frontend Framework | React + TypeScript | 18 / 5 | React, Angular, Vue, Svelte | Team skills; component ecosystem; state management maturity | React version churn discipline required | MIT | ADR-014
T-016 | State Management (FE) | Redux Toolkit + RTK Query | 2+ | Redux Toolkit, Zustand, Jotai, TanStack Query | Mature; devtools; predictable for large app | Learning curve for newer FE devs | MIT | -
T-017 | Testing - Unit/Integration | JUnit 5 + Testcontainers | 5 / 1.19+ | JUnit, TestNG, Spock | Standard Java testing; Testcontainers for integration realism | - | EPL-2.0 / MIT | -
T-018 | Testing - Performance | k6 + Gatling | latest | k6, Gatling, JMeter, Locust | k6 for modern scripting; Gatling for JVM-native stress | - | AGPL / Apache 2.0 | -
T-019 | Schema Migration | Flyway OSS | 10+ | Flyway, Liquibase | Forward-only discipline; simpler mental model | No rollback via tool; compensating migrations required | Apache 2.0 (OSS edition) | ADR-016
T-020 | Virtualization | VMware vSphere | 8+ | VMware, KVM/oVirt, Proxmox | Existing enterprise standard; not a fresh decision | Broadcom licensing trajectory | Commercial | - | Existing infrastructure

## 6. Design Reviews
Design Authority Board (DAB) Log
Weekly standing DAB meetings. Significant ADRs, integration contracts, and safety-critical designs reviewed here.
External architect independent review recommended at 3-month mark; capture in this log.
Session # | Date | Topics / ADRs Reviewed | Participants | Decisions Made | Action Items | Next Review Date | Minutes Link | Chair
DAB-001 | 2026-01-22 | ADR-001, ADR-002 initial discussion | Chief Arch, Sr Eng Deputy, 3 Sr Engs, Infra Arch, Sec Arch | Both ADRs moved to Accepted; Sr Engs concur | Publish to wiki; socialize with squads | 2026-01-29 | wiki/dab/001 | Chief Arch
DAB-002 | 2026-01-29 | ADR-003 (Kafka), ADR-004 (Redis) | Chief Arch, Sr Eng Deputy, 3 Sr Engs, Platform TL | Both accepted; SP-01 triggered for Kafka capacity validation | SP-01 owner Sr Eng A | 2026-02-05 | wiki/dab/002 | Chief Arch
DAB-003 | 2026-02-05 | ADR-005 (VM deployment), ADR-006 (outbox pattern) | Chief Arch, Sr Eng Deputy, Sr Engs, Integration Arch, Product Council op | Both accepted; outbox marked safety-critical; Product Council sign-off received | Define outbox library vs custom via SP-10 | 2026-02-12 | wiki/dab/003 | Chief Arch
DAB-004 | 2026-02-12 | ADR-007 (audit), ADR-008 (CQRS) | Chief Arch, Sr Eng Deputy, Sr Engs, Sec Arch, Data Arch | Both accepted; audit safety-critical with Product Council sign-off | Schema design for audit store; SP-04 for CQRS | 2026-02-19 | wiki/dab/004 | Chief Arch
DAB-005 | 2026-02-19 | ADR-009 (SSO), ADR-010 (RBAC) | Chief Arch, Sr Eng Deputy, Sec Arch, IAM team liaison, Product Council op | Both accepted; RBAC safety-critical due to override logging | IAM integration plan; role catalog | 2026-02-26 | wiki/dab/005 | Chief Arch
DAB-006 | 2026-02-26 | ADR-011 (Vault), ADR-012 (observability) | Chief Arch, Sr Eng Deputy, Sr Engs, Platform TL, Sec Arch | Both accepted | Vault cluster design; dashboard baseline | 2026-03-05 | wiki/dab/006 | Chief Arch
DAB-007 | 2026-03-05 | ADR-013 (modular monolith + services), ADR-014 (React) | Chief Arch, Sr Eng Deputy, Sr Engs, FE Tech Lead | Both accepted; decomposition into services captured in DG-002 | Container diagram update; DG-002 v1.0 | 2026-03-12 | wiki/dab/007 | Chief Arch
DAB-008 | 2026-03-12 | ADR-015 (REST+gRPC), ADR-016 (Flyway) | Chief Arch, Sr Eng Deputy, Integration Arch, DBA | Both accepted | Internal gRPC standards; Flyway dev workflow | 2026-03-19 | wiki/dab/008 | Chief Arch
DAB-009 | 2026-03-19 | ADR-017 initial (switching step state machine library) | Chief Arch, Sr Eng Deputy, Sr Eng (safety-focused), Product Council | Under Review; SP-06 required first | SP-06 execution; re-review in DAB-011 | 2026-03-26 | wiki/dab/009 | Chief Arch
DAB-010 | 2026-03-26 | ADR-018 initial (reporting replica isolation) | Chief Arch, Sr Eng Deputy, DBA, Reporting PO | Under Review; SP-11 required | SP-11 execution | 2026-04-02 | wiki/dab/010 | Chief Arch
DAB-011 | 2026-04-02 | ADR-019 initial (migration), ADR-020 initial (CIP boundary) | Chief Arch, Sr Eng Deputy, Data Architect, Sec Arch, Compliance Officer, Product Council | Both proposed; require external architect review | External architect engagement scheduled | 2026-04-09 | wiki/dab/011 | Chief Arch
DAB-012 | 2026-04-09 | External Architect Independent Review session | Chief Arch, Sr Eng Deputy, External Architect, Program Manager, Sponsor rep | External review findings captured | Address findings; re-review at DAB-015 | 2026-04-16 | wiki/dab/012 | External Architect

## 7. Cross-Cutting Matrix
Cross-Cutting Concern Design Matrix
For each component, how are audit / observability / security / resilience / compliance concerns addressed?
Empty cells indicate design gaps. All cells populated before component enters Build.
Component | Type | Audit Approach | Observability Approach | Security Approach | Resilience Approach | Compliance (NERC CIP) | Notes
SCADA Ingestion Service | Service | Event-source; all ingested events persisted immutably | Kafka consumer lag metrics; ingestion rate; error rate; trace of each event | Service account; encrypted Kafka cluster; mTLS to SCADA | Kafka replication factor 3; producer retries; consumer resumption from last-committed offset | Events crossing CIP boundary identified; EAP logging
Integration Gateway Service | Service | Inbound and outbound API calls logged | Request rate, latency, error rate per integration; circuit breaker status | mTLS; per-integration service accounts; rotation via Vault | Circuit breaker per integration; retry with backoff; idempotency keys | Field work system crosses CIP boundary — review required
Card Module (monolith) | Module | Outbox for all state transitions; audit record per transition | Card creation rate; active card count; state-transition latency | RBAC with district scope enforcement; audit event context | Transactional boundaries for consistency; event emission after commit | Not in CIP scope (Distribution)
Switching Order Module (monolith) | Module | State transition audit; precondition evaluation audit; override audit | Order count by state; authoring duration; execution duration; failure rate | RBAC; supervisor override authorization; authorization context in audit | Transaction boundaries per step; compensating actions | Transmission orders in CIP scope; additional audit trail | Safety-critical
Switching Step Module (monolith) | Module | Precondition evaluation audit; postcondition verification audit; override audit | Step execution rate; precondition failure rate; override rate | RBAC; override authorization; grounding rule enforcement | State machine recovery after restart; postcondition timeout handling | Transmission steps in CIP scope | Safety-critical; highest rigor
Clearance Module (monolith) | Module | Issuance/release audit; device-scope audit | Active clearance count; issuance rate; scope overlap rate | RBAC; device-scope enforcement; electronic attestation | Transaction boundaries; no-overlap invariant enforcement | CIP applicability for transmission | Safety-critical
Audit Service | Service | (is the audit) immutable append-only log | Ingestion rate; query latency; storage consumption | Write-only API; read restricted to compliance roles | Replication to DR; cold storage archival | 7+ year retention; audit integrity controls | Referenced by all components
Reporting Service | Service | Read-only query audit for sensitive queries | Query performance; replica lag; report generation time | RBAC; row-level security for customer data | Replica read isolation; graceful degradation if replica lag | Reports may touch CIP info
Notification Service | Service | Notification send audit | Send rate; failure rate; delivery latency | Service account; template sanitization | Retry with backoff; dead letter queue | No CIP applicability unless notification content includes BES CSI
Frontend (Operator UI) | Client | User action audit emitted via API | Page load time; RUM; error rate; feature adoption | Session management; CSRF; content security policy; XSS controls | Offline indication; retry on transient backend failures | No local storage of CIP data | WCAG 2.2 AA
Enterprise Auth Integration | Integration | Auth event forwarded to SIEM | Auth success/failure rate; MFA rate; session duration | SAML/OIDC with IdP; MFA enforced for privileged | Cached credentials window for IdP outage | CIP personnel training linked; access authorization records
Field Work Integration | Integration | Dispatch and status change audit | Dispatch throughput; ack latency; reconciliation drift | mTLS; API key via Vault; rotation schedule | Outbox pattern; idempotency; retry; reconciliation job | Crosses boundary to Field Work System — review CIP

## 8. Integration Contracts
Integration Contract Register
Per-integration signed contract covering schema, semantics, SLAs, error handling.
Contract must be signed by both sides (our program + integration counterparty) before story implementation begins.
Contract ID | Integration | Direction | Protocol/Format | Version | Schema Location | Our Signatory | Counterparty Signatory | Signed Date | Status | Notes
INT-01 | SCADA/EMS | Inbound (event stream) | Kafka / IEC 61850 encoded | 1.0 | wiki/contracts/scada-v1 | Integration Architect | SCADA team lead |  | In Review | Based on P1-07 output
INT-02 | Field Work System | Outbound (dispatch) + Inbound (status) | REST / JSON | 1.0 | wiki/contracts/fieldwork-v1 | Integration Architect | Field Work vendor PM |  | Draft
INT-03 | GIS | Inbound (topology sync) | REST / JSON | 1.0 | wiki/contracts/gis-v1 | Integration Architect | GIS team lead |  | Draft | Retirement roadmap under discussion
INT-04 | CIS | Outbound (lookup) + batch (impact calc) | REST / JSON + SFTP batch | 1.0 | wiki/contracts/cis-v1 | Integration Architect | CIS team lead |  | Draft
INT-05 | Enterprise SSO (SAML) | Inbound (auth) | SAML 2.0 | n/a | wiki/contracts/sso-v1 | Security Architect | IAM team lead |  | In Review | Metadata exchange
INT-06 | Enterprise SIEM | Outbound (log forward) | Syslog | 1.0 | wiki/contracts/siem-v1 | Security Architect | SIEM team lead |  | Draft | For NERC CIP evidence
INT-07 | Asset Mgmt (Maximo) | Bidirectional (asset sync) | REST / JSON + scheduled | 1.0 | wiki/contracts/am-v1 | Integration Architect | Asset Mgmt team lead |  | Not Started | Post-MVP scope
INT-08 | Customer Notification System | Outbound (notifications) | REST / JSON | 1.0 | wiki/contracts/cns-v1 | Integration Architect | CX team lead |  | Not Started | Post-MVP
INT-09 | Outage Map (public) | Outbound (outage data) | REST / JSON | 1.0 | wiki/contracts/omap-v1 | Integration Architect | Digital team lead |  | Not Started | Post-MVP
INT-10 | Enterprise Vault (secrets) | Outbound (secret fetch) | HTTPS / Vault API | n/a | wiki/contracts/vault-v1 | Platform Tech Lead | IAM team lead |  | In Review

## 9. Data Migration Plan
Data Migration Plan (per entity/domain)
Each row: one entity/domain. Approach from ADR-019; dress rehearsal target 3+ per entity.
Reconciliation approach mandatory for operational entities.
Migration ID | Entity/Domain | Legacy Source | Target Schema | Est. Row Count | Approach | Cleansing Required | Validation Approach | Dress Rehearsals Planned | Rehearsals Completed | Status | Notes
MIG-01 | Device Catalog - Distribution | legacy/assets.dbo.device | assets.device | 45000 | One-time ETL | Moderate (code mapping) | Row count + hash + sample check | 3 | 0 | Design
MIG-02 | Device Catalog - Transmission | legacy/assets.dbo.device_trans | assets.device (trans) | 8500 | One-time ETL | Moderate | Row count + hash + CIP review | 3 | 0 | Design | CIP-scoped
MIG-03 | Device Catalog - Di-Electric | legacy/dielectric.dbo.fluid_dev | assets.device (de) | 1200 | One-time ETL | Low | Row count + sample check | 3 | 0 | Backlog
MIG-04 | Device Catalog - RTU/Telephonic | legacy/rtu.dbo.comms_dev | assets.device (rtu) | 3400 | One-time ETL | Low | Row count + sample check | 3 | 0 | Backlog
MIG-05 | Device Catalog - Steam | legacy/steam.dbo.steam_dev | assets.device (st) | 800 | One-time ETL | Low | Row count + sample check | 3 | 0 | Backlog
MIG-06 | Customer-Feeder Mapping | legacy/cis_link.dbo.cust_feeder | ops.customer_feeder | 2800000 | One-time ETL + daily delta | High (null refs, duplicates) | Total count + district-level reconciliation | 3 | 0 | Design | CIS continues as authority
MIG-07 | Historical Cards (5 years) | legacy/oms.dbo.card + linked | ops.card_history | 1250000 | Phased by year; newest first | High | Per-year reconciliation | 3 | 0 | Backlog | Separate from active cards
MIG-08 | Historical Switching Orders | legacy/swman.dbo.swo + steps | ops.swo_history | 180000 | Phased by year | High | Per-year reconciliation | 3 | 0 | Backlog
MIG-09 | Historical Clearances | legacy/clr.dbo.clearance | ops.clearance_history | 120000 | Phased | Moderate | Per-year reconciliation | 3 | 0 | Backlog
MIG-10 | User Accounts (names + roles) | legacy/auth.dbo.user_role | iam.user_role | 420 | One-time sync + future SSO | High (role mapping) | 1:1 reconciliation + role validation | 2 | 0 | Design
MIG-11 | Audit Records (NERC CIP retention) | legacy/audit.dbo.audit_log | audit.event | 18000000 | Phased ELT; preserve timestamps | Moderate | Hash validation; count per day | 3 | 0 | Backlog | 7+ year retention required
MIG-12 | Switching Templates | legacy/swman.dbo.template | ops.switching_template | 850 | One-time + review | Moderate | Review + operator validation | 2 | 0 | Design | Product Council review required
MIG-13 | Reference Data (all domains) | various reference tables | reference.* | 15000 | One-time + future manual sync | Moderate | Full review; hash check | 2 | 0 | Design
MIG-14 | Active Cards at Cutover | legacy/oms.dbo.card (active) | ops.card | 1500 | Trickle sync during parallel run | Low | Real-time divergence monitoring | 5 | 0 | Design | Highest discipline; per-district cutover
MIG-15 | Active Switching Orders at Cutover | legacy/swman.dbo.swo (active) | ops.swo | 250 | Trickle sync | Low | Real-time divergence monitoring | 5 | 0 | Design | Per-district cutover

## 10. NERC CIP Register
NERC CIP Applicability Register
Component-by-component determination of CIP applicability. BES Cyber System scoping and impact rating per CIP-002.
Compliance Officer + Security Architect sign each determination.
Component ID | Component | BES Cyber System? | Impact Rating | In ESP? | In PSP? | Applicable CIP Standards | Determination Rationale | Evidence Artifacts | Sign-off | Notes
CIP-001 | SCADA Ingestion Service | Y (associated) | Medium | Y | Y | CIP-003,004,005,007,008,009,010,011,013 | Handles BES operational data; resides in operational network | Asset register; ESP/EAP diagram; access control lists | Pending | Highest CIP scrutiny
CIP-002 | Integration Gateway Service (Transmission) | Y (associated) | Medium | Y | Y | CIP-003,004,005,007,010,011 | Transmission integration traffic; data touches BES | Same as above | Pending
CIP-003 | Integration Gateway Service (Distribution) | N | n/a | N | Y | - | Distribution-only path; no BES applicability | Logical separation evidence | Pending | Physical co-location with PSP controls
CIP-004 | Switching Order Module (Transmission portion) | Y | Medium | Y | Y | CIP-003,004,005,007,008,009,010,011 | Operates BES Cyber Assets; affects BES reliability | Component design evidence; access controls | Pending | Safety-critical and CIP-scoped
CIP-005 | Switching Step Module (Transmission portion) | Y | Medium | Y | Y | CIP-003,004,005,007,008,009,010,011 | Same as above | Component design evidence; access controls | Pending | Safety-critical and CIP-scoped
CIP-006 | Clearance Module (Transmission portion) | Y | Medium | Y | Y | CIP-003,004,005,007,008,009,010,011 | Same as above | Component design evidence; access controls | Pending
CIP-007 | Card Module | N | n/a | N | Y | - | Distribution-dominant; tactical data only | Segregation evidence | Pending | Review if transmission operators use
CIP-008 | Audit Service | Y (associated) | Medium | Y | Y | CIP-007,008,010,011 | Stores CIP-evidence audit records; integrity critical | Immutability controls; access logs | Pending
CIP-009 | Primary PostgreSQL Cluster | Y (associated) | Medium | Y | Y | CIP-003,004,005,007,010,011 | Stores BES operational data | DB HA docs; access controls; patch records | Pending
CIP-010 | Kafka Cluster | Y (associated) | Medium | Y | Y | CIP-003,004,005,007,010,011 | Carries BES event traffic | Cluster topology; access controls; patch records | Pending
CIP-011 | Enterprise SIEM integration | Y (associated) | Medium | Y | Y | CIP-007,008,010,011 | Receives CIP evidence | Forwarding config; retention records | Pending
CIP-012 | Reporting Service | N | n/a | N | Y | - | Read-only; replica separated; no operational impact | Architecture evidence | Pending | Some reports may contain CIP info
CIP-013 | Operator Workstations | Y (associated) | Medium | Y | Y | CIP-004,005,006,007,010,011 | Used to access BES Cyber Systems | Workstation hardening; MFA; access records | Pending | Existing workstation program
CIP-014 | Development/Test environments | N | n/a | N | N | - | Isolated from production; no BES data | Network segregation evidence | Pending | Confirm data isolation

## 11. Design Risks
Design Phase Risk Log
Phase 2-specific risks (distinct from program-level risks). Resolution or mitigation required before Design phase exit.
Any CRITICAL risk open at Design phase exit blocks DAB sign-off.
Risk ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status | Notes
DR-001 | Chief Architect unintentionally imports legacy patterns via design artifacts | 4 | 4 | 16 | Dual-signature discipline; P2-05 legacy pattern check per artifact; external architect independent review | Sr Eng Deputy | Active | Counterpart to program risk R-002
DR-002 | ADR backlog grows faster than DAB throughput; decisions delayed | 3 | 4 | 12 | Weekly DAB cadence; batched related ADRs; pre-DAB async review | Program Manager | Active
DR-003 | External architect review findings require significant rework | 3 | 3 | 9 | Schedule review at 3-month mark while adjustable; frame as helpful check not audit | Chief Architect | Active
DR-004 | NERC CIP boundary determinations disputed by Compliance Officer | 2 | 4 | 8 | Early Compliance engagement; conservative posture; documented rationale | Security Architect | Active
DR-005 | Integration contract negotiations with Field Work vendor stall | 3 | 4 | 12 | Escalation path defined; alternative (batch-only interim) identified | Integration Architect | Active
DR-006 | State machine formalization reveals inconsistencies with existing business rules | 3 | 3 | 9 | Expected and acceptable; drives rule review cycle with Product Council | Chief Architect | Active
DR-007 | Spike budget overruns dilute Design phase velocity | 3 | 3 | 9 | Strict time-box; halt-and-capture if exceeded; spike postmortems | Program Manager | Active
DR-008 | Legacy code archaeology (vendor) reveals undocumented rules that reshape design | 4 | 3 | 12 | Expected and planned-for; Design iteration built into schedule | Data Architect | Active
DR-009 | Product Council operators unavailable for safety-critical sign-offs due to operational demands | 3 | 4 | 12 | Scheduled sessions; advance notice; backup operator identified per area | Program Manager | Active
DR-010 | Senior engineer deputy capacity split between design and senior mentoring | 3 | 3 | 9 | Explicit time allocation; mentoring pair-up to share load | Program Manager | Active
DR-011 | Design outputs don't decompose cleanly to stories for Build | 3 | 4 | 12 | Epic → Story decomposition via P2-01/P2-02 during design; verify testability | POs + Sr Engs | Active
DR-012 | Data migration approach proves infeasible for active cards at cutover | 2 | 5 | 10 | Dress rehearsals starting in Phase 3; fallback to bulk cutover approach if trickle-sync fails | Data Migration Lead | Active