## README
Phase 3 — Build
Purpose | Deliver MVP and subsequent increments through sprint-by-sprint execution with sustained quality.
Duration | 10-18 months. MVP complete by Month 16; full scope by Month 34.
Sprint cadence | 2-week sprints. Sprint zero runs overlapping final Design weeks for squad formation.
Squads | 4 squads aligned to epic streams: Ops Core, Switching Safety, Integration & Data, Platform & Observability. Each squad ~6-8 people led by a Sr Eng.
Entry criteria | MVP ADRs accepted. MVP Epics decomposed to initial story level. Platform foundation operational. Definition of Ready and Definition of Done agreed.
Exit criteria | MVP in UAT, remaining scope nearing complete, parallel-run decisions informed by actual performance.
Tabs
1. Story Backlog | All stories across all epics. Status progresses Backlog → Refined → Ready → In Sprint → In Test → Done.
2. Sprint Backlog | Active sprint + next two sprints. Detailed commitment and progress.
3. Capacity Calculator | Per-sprint team capacity factoring allocation, PTO, ceremonies.
4. Velocity Tracker | Sprint velocity history with trend.
5. Sprint Retrospectives | Keep / Stop / Start items and actions across sprints.
6. Impediment Log | Blockers preventing progress. Owner and escalation path.
7. Feature Flag Register | Flags, enablement schedule, per-district rollout state.
8. Tech Debt Register | Deferred work with paydown priority.
9. Code Review Findings | Systemic patterns from code review prompts worth tracking.
10. Build Phase Risks | Build-specific risks distinct from program risks.
11. Build Dashboard | KPI roll-up: velocity, defect escape, AC coverage, tech debt trend.
Discipline
Definition of Ready | INVEST-checked; Gherkin AC present; size estimated; dependencies resolved; safety-critical Product Council informed.
Definition of Done | Code merged; tests passing; AC demonstrated; code reviewed; docs updated; audit events verified; feature flag configured if applicable; observability instrumentation present.
Safety-critical gating | Safety-critical stories pair-programmed. Code review by Sr Eng + safety-aware reviewer. Product Council demo before accepting.
Tech debt limit | Tech debt ratio capped at 15% of story points. Exceeding triggers paydown sprint or scope decision.
Rotations | Junior and mid engineers rotate across squads on a 2-sprint cadence. Seniors anchor. Prevents knowledge silos.

## 1. Story Backlog
Story Backlog (program-wide)
All stories across all Epics. Status advances Backlog → Refined → Ready → In Sprint → In Test → Done.
Story IDs: US-[EPIC-SHORT]-[NUMBER]. Safety-critical stories require pair-program + dual review + Product Council demo.
Story ID | Title | Epic | Squad | Priority | Safety-Critical? | Points | Status | Sprint | Assignee | DoR Check | DoD Check | Dependencies | Notes
US-SCADA-001 | Consume SCADA event stream with consumer groups | E-OPS-01 | Integration & Data | Must | N | 8 | Done | S-01 | Eng-A1 | Y | Y | Platform foundation ready
US-SCADA-002 | Deduplicate events within sliding 15-minute window | E-OPS-01 | Integration & Data | Must | N | 5 | Done | S-02 | Eng-A2 | Y | Y | US-SCADA-001
US-SCADA-003 | Parse and validate IEC 61850 event schema | E-OPS-01 | Integration & Data | Must | N | 5 | Done | S-02 | Eng-A2 | Y | Y | INT-01 signed
US-SCADA-004 | Correlate events to known devices via device catalog | E-OPS-01 | Integration & Data | Must | N | 8 | In Test | S-03 | Eng-A1 | Y | N | MIG-01 device catalog loaded
US-SCADA-005 | Handle orphan events (no device match) | E-OPS-01 | Integration & Data | Must | N | 5 | In Sprint | S-04 | Eng-A3 | Y | N | US-SCADA-004
US-SCADA-006 | Event replay on consumer restart | E-OPS-01 | Integration & Data | Must | N | 5 | In Sprint | S-04 | Eng-A2 | Y | N | US-SCADA-001
US-SCADA-007 | Daily reconciliation: detect state divergence from SCADA | E-OPS-01 | Integration & Data | Must | N | 13 | Ready | S-05 | Eng-A1 | Y | N | FM-13 mitigation
US-CARD-001 | Auto-create card from qualifying SCADA fault event | E-OPS-02 | Ops Core | Must | N | 8 | Done | S-02 | Eng-B2 | Y | Y | US-SCADA-004
US-CARD-002 | Manual card creation by operator | E-OPS-02 | Ops Core | Must | N | 5 | Done | S-02 | Eng-B3 | Y | Y | SM-01 formalized
US-CARD-003 | Bulk card open during storm event | E-OPS-02 | Ops Core | Must | N | 8 | Done | S-03 | Eng-B2 | Y | Y | US-CARD-001 | Feature-flagged
US-CARD-004 | Card state transitions (Open through Closed) | E-OPS-02 | Ops Core | Must | N | 13 | Done | S-03 | Eng-B1 | Y | Y | SM-01 | Complex state machine
US-CARD-005 | Card assignment to operator | E-OPS-02 | Ops Core | Must | N | 3 | In Test | S-04 | Eng-B3 | Y | N | US-CARD-004
US-CARD-006 | Add notes and attachments to card | E-OPS-02 | Ops Core | Should | N | 5 | In Sprint | S-04 | Eng-B4 | Y | N | Cross-cutting attachment service
US-CARD-007 | Link cards (parent/child relationships) | E-OPS-02 | Ops Core | Must | N | 5 | Ready | S-05 | Eng-B2 | Y | N | US-CARD-004
US-CARD-008 | Card detail view UI | E-OPS-02 | Ops Core | Must | N | 8 | Ready | S-05 | Eng-FE1 | Y | N | US-CARD-004
US-CARD-009 | Close card with cause code selection | E-OPS-02 | Ops Core | Must | N | 5 | Refined | S-06 | Eng-B3 | N | N | Cause code catalog migrated
US-CARD-010 | Card reopen workflow with reason capture | E-OPS-02 | Ops Core | Must | N | 5 | Refined | S-06 | Eng-B3 | N | N | US-CARD-009
US-SWEXEC-001 | Start switching order execution | E-OPS-04 | Switching Safety | Must | Y | 8 | In Sprint | S-04 | Eng-C1+Eng-C2 | Y | N | SM-02, SM-03 finalized | Pair-program
US-SWEXEC-002 | Execute step with precondition verification | E-OPS-04 | Switching Safety | Must | Y | 13 | Ready | S-05 | Eng-C1+Eng-C3 | Y | N | BR-SW-042 safety-critical | Pair-program
US-SWEXEC-003 | Mark step complete with postcondition check | E-OPS-04 | Switching Safety | Must | Y | 13 | Ready | S-05 | Eng-C1+Eng-C2 | Y | N | SCADA telemetry integration | Pair-program
US-SWEXEC-004 | Pause and resume switching order | E-OPS-04 | Switching Safety | Must | Y | 8 | Refined | S-06 | Eng-C1+Eng-C3 | N | N | US-SWEXEC-001 | Pair-program
US-SWEXEC-005 | Reverse completed steps (abandonment) | E-OPS-04 | Switching Safety | Must | Y | 13 | Refined | S-07 | Eng-C1+Eng-C2 | N | N | G-003 resolved | Pair-program
US-SWEXEC-006 | Supervisor override of precondition with reason | E-OPS-04 | Switching Safety | Must | Y | 8 | Refined | S-07 | Eng-C1+Eng-C3 | N | N | BR-SW-050 override policy | Pair-program; absolute BRs blocked
US-SWEXEC-007 | Shift handoff during active switching order | E-OPS-04 | Switching Safety | Should | Y | 8 | Backlog | S-08 |  | N | N | US-SWEXEC-001, FM-10 addressed
US-CLR-001 | Issue clearance for device(s) | E-OPS-05 | Switching Safety | Must | Y | 8 | Ready | S-06 | Eng-C4 | Y | N | SM-04 finalized
US-CLR-002 | Release clearance with crew acknowledgment | E-OPS-05 | Switching Safety | Must | Y | 5 | Refined | S-06 | Eng-C4 | N | N | US-CLR-001
US-CLR-003 | Check clearance scope overlap invariant | E-OPS-05 | Switching Safety | Must | Y | 8 | Refined | S-07 | Eng-C4+Eng-C2 | N | N | No-overlap invariant from SM-04 | Safety-critical invariant
US-CLR-004 | Clearance audit retrieval view | E-OPS-05 | Switching Safety | Must | Y | 5 | Backlog | S-08 |  | N | N | US-CLR-001, audit service
US-FWS-001 | Dispatch work order via outbox pattern | E-INT-02 | Integration & Data | Must | N | 8 | Ready | S-05 | Eng-A3 | Y | N | INT-02 signed, ADR-006
US-FWS-002 | Idempotent retry with exponential backoff | E-INT-02 | Integration & Data | Must | N | 5 | Ready | S-06 | Eng-A3 | Y | N | US-FWS-001
US-FWS-003 | Receive field status updates | E-INT-02 | Integration & Data | Must | N | 5 | Refined | S-06 | Eng-A2 | N | N | INT-02 signed
US-FWS-004 | Reconciliation job for dispatch drift | E-INT-02 | Integration & Data | Must | N | 8 | Backlog | S-08 |  | N | N | US-FWS-001
US-AUTH-001 | SAML SSO authentication flow | E-PLT-01 | Platform & Observability | Must | N | 8 | Done | S-01 | Eng-D1 | Y | Y | INT-05 signed
US-AUTH-002 | RBAC role assignment and enforcement | E-PLT-01 | Platform & Observability | Must | N | 13 | Done | S-02 | Eng-D1 | Y | Y | Role catalog
US-AUTH-003 | District-scope attribute enforcement | E-PLT-01 | Platform & Observability | Must | Y | 8 | Done | S-03 | Eng-D1 | Y | Y | ADR-010
US-AUTH-004 | Supervisor override authorization with step-up MFA | E-PLT-01 | Platform & Observability | Must | Y | 8 | In Test | S-04 | Eng-D1 | Y | N | US-AUTH-002, US-AUTH-003
US-AUDIT-001 | Event-sourced audit log append API | E-PLT-02 | Platform & Observability | Must | Y | 8 | Done | S-01 | Eng-D2 | Y | Y | ADR-007
US-AUDIT-002 | Audit event schema and versioning | E-PLT-02 | Platform & Observability | Must | Y | 5 | Done | S-01 | Eng-D2 | Y | Y
US-AUDIT-003 | Audit retrieval API with time/actor/target query | E-PLT-02 | Platform & Observability | Must | Y | 8 | In Test | S-03 | Eng-D2 | Y | N | US-AUDIT-001
US-AUDIT-004 | Immutability controls on audit store | E-PLT-02 | Platform & Observability | Must | Y | 5 | Done | S-02 | Eng-D2 | Y | Y | DB hardening
SUMMARY
Total stories: | -394
Safety-critical: | 17
Total points: | 300
Done: | 13
In Test: | 4
In Sprint: | 4
Ready: | 8
Done points: | 99
% Done (by points): | 33%
Blocked: | 0

## 2. Sprint Backlog
Sprint Backlog — active + next two sprints
Focused view of current execution. Full backlog lives in tab 1.
Status progresses: To Do → In Progress → In Review → In Test → Done. Daily standup updates these.
Sprint | Story ID | Title | Assignee | Squad | Points | Task Status | Hrs Remaining | Blockers | Notes
S-04 | US-SCADA-005 | Handle orphan events | Eng-A3 | Integration & Data | 5 | In Progress | 6
S-04 | US-SCADA-006 | Event replay on consumer restart | Eng-A2 | Integration & Data | 5 | In Review | 2 |  | PR #284
S-04 | US-CARD-005 | Card assignment to operator | Eng-B3 | Ops Core | 3 | In Test | 0
S-04 | US-CARD-006 | Add notes and attachments to card | Eng-B4 | Ops Core | 5 | In Progress | 8 | Attachment service API
S-04 | US-SWEXEC-001 | Start switching order execution | Eng-C1+Eng-C2 | Switching Safety | 8 | In Progress | 18 |  | Pair-programmed
S-04 | US-AUTH-004 | Supervisor override with step-up MFA | Eng-D1 | Platform & Observability | 8 | In Test | 0 |  | Product Council demo scheduled
S-04 | US-OBS-003 | SCADA consumer lag dashboard | Eng-D3 | Platform & Observability | 3 | In Review | 1 |  | PR #290
S-04 | US-CARD-011 | Card priority escalation rule | Eng-B2 | Ops Core | 3 | Done | 0
S-04 | TS-01 | Reduce flaky SCADA integration test | Eng-A1 | Integration & Data | 2 | Done | 0 |  | Tech debt pay-down
S-05 | US-SCADA-007 | SCADA reconciliation job | Eng-A1 | Integration & Data | 13 | To Do | 40 |  | SP-11 input
S-05 | US-CARD-007 | Link cards parent/child | Eng-B2 | Ops Core | 5 | To Do | 16
S-05 | US-CARD-008 | Card detail view | Eng-FE1 | Ops Core | 8 | To Do | 24
S-05 | US-SWEXEC-002 | Execute step with precondition | Eng-C1+Eng-C3 | Switching Safety | 13 | To Do | 40 |  | Pair-programmed; BR-SW-042
S-05 | US-SWEXEC-003 | Mark step complete with postcondition | Eng-C1+Eng-C2 | Switching Safety | 13 | To Do | 40 |  | Pair-programmed
S-05 | US-FWS-001 | Dispatch via outbox pattern | Eng-A3 | Integration & Data | 8 | To Do | 24
S-06 | US-CARD-009 | Close card with cause code | Eng-B3 | Ops Core | 5 | To Do | 0 |  | Refinement needed
S-06 | US-CARD-010 | Card reopen workflow | Eng-B3 | Ops Core | 5 | To Do | 0 |  | Refinement needed
S-06 | US-SWEXEC-004 | Pause and resume switching order | Eng-C1+Eng-C3 | Switching Safety | 8 | To Do | 0 |  | Pair-programmed
S-06 | US-CLR-001 | Issue clearance for device | Eng-C4 | Switching Safety | 8 | To Do | 0
S-06 | US-CLR-002 | Release clearance | Eng-C4 | Switching Safety | 5 | To Do | 0
S-06 | US-FWS-002 | Idempotent retry | Eng-A3 | Integration & Data | 5 | To Do | 0
S-06 | US-FWS-003 | Receive field status updates | Eng-A2 | Integration & Data | 5 | To Do | 0
CURRENT SPRINT (S-04)
Points committed: | 42
Points done: | 5
% complete: | 11.9%
Hrs remaining: | 35

## 3. Capacity Calculator
Sprint Capacity Calculator
Capacity per sprint factoring team roster, allocation %, PTO, holidays, ceremonies.
Update allocation per sprint. Points capacity = (available hours / focus factor) — focus factor calibrated from velocity data.
Person / Role | Squad | Hrs/Day | Allocation % | Sprint Days | PTO Days | Ceremony Hrs | Avail Hrs | Hrs/Point (calibrated) | Pts Capacity | Notes
Chief Architect | Cross-squad | 8 | 10 | 10 | 0 | 8 | 0 | 8 | 0 | Design oversight
Sr Eng Deputy | Cross-squad | 8 | 30 | 10 | 0 | 10 | 14 | 8 | 1.75 | Mentoring + reviews
Sr Eng A (Int&Data lead) | Integration & Data | 8 | 80 | 10 | 0 | 10 | 54 | 7 | 7.7143
Sr Eng B (Ops Core lead) | Ops Core | 8 | 80 | 10 | 0 | 10 | 54 | 7 | 7.7143
Sr Eng C (Switching lead) | Switching Safety | 8 | 80 | 10 | 0 | 10 | 54 | 7 | 7.7143 | Safety-critical focus
Sr Eng D (Platform lead) | Platform & Observability | 8 | 80 | 10 | 0 | 10 | 54 | 7 | 7.7143
Mid Eng 1 | Integration & Data | 8 | 90 | 10 | 1 | 6 | 58.8 | 8 | 7.35
Mid Eng 2 | Integration & Data | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
Mid Eng 3 | Ops Core | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
Mid Eng 4 | Ops Core | 8 | 90 | 10 | 2 | 6 | 51.6 | 8 | 6.45 | PTO S-04
Mid Eng 5 | Switching Safety | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
Mid Eng 6 | Platform & Observability | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
Jr Eng 1 | Integration & Data | 8 | 80 | 10 | 0 | 6 | 58 | 10 | 5.8 | Ramping
Jr Eng 2 | Ops Core | 8 | 80 | 10 | 0 | 6 | 58 | 10 | 5.8 | Ramping
Jr Eng 3 | Switching Safety | 8 | 80 | 10 | 0 | 6 | 58 | 10 | 5.8 | Ramping
Jr Eng 4 | Platform & Observability | 8 | 80 | 10 | 0 | 6 | 58 | 10 | 5.8 | Ramping
FE Tech Lead | Ops Core | 8 | 70 | 10 | 0 | 8 | 48 | 7 | 6.8571
FE Dev 1 | Ops Core | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
FE Dev 2 | Switching Safety | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
FE Dev 3 | Platform & Observability | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
QA Auto 1 | Cross-squad | 8 | 80 | 10 | 0 | 6 | 58 | 6 | 9.6667 | Ops Core + Switching
QA Auto 2 | Cross-squad | 8 | 80 | 10 | 0 | 6 | 58 | 6 | 9.6667 | Integration + Platform
Integration Eng 1 | Integration & Data | 8 | 80 | 10 | 0 | 6 | 58 | 7 | 8.2857
Integration Eng 2 | Integration & Data | 8 | 80 | 10 | 0 | 6 | 58 | 7 | 8.2857
DBA | Cross-squad | 8 | 40 | 10 | 0 | 4 | 28 | 8 | 3.5
DevOps 1 | Platform & Observability | 8 | 60 | 10 | 0 | 6 | 42 | 8 | 5.25
DevOps 2 | Platform & Observability | 8 | 60 | 10 | 0 | 6 | 42 | 8 | 5.25
Sec Eng | Cross-squad | 8 | 30 | 10 | 0 | 4 | 20 | 8 | 2.5
BA 1 | Ops Core + Switching | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
BA 2 | Integration + Platform | 8 | 90 | 10 | 0 | 6 | 66 | 8 | 8.25
SQUAD CAPACITY
Integration & Data | [6 empty] | 352.8 |  | 45.6857
Ops Core | [6 empty] | 409.6 |  | 51.5714
Switching Safety | [6 empty] | 244 |  | 30.0143
Platform & Observability | [6 empty] | 328 |  | 40.5143
Cross-squad | [6 empty] | 178 |  | 27.0833
TOTAL TEAM | [6 empty] | 1578.4 |  | 203.119

## 4. Velocity Tracker
Velocity Tracker
Sprint-by-sprint velocity history. Use 3-sprint rolling average for commitment forecasts.
Committed vs. Completed gap indicates estimation accuracy; widening gap is a signal to investigate.
Sprint | Start Date | End Date | Committed Pts | Completed Pts | Delta | Completed Stories | Carry-over Stories | Defects Escaped | Notes
S-00 | 2026-07-06 | 2026-07-17 | 0 | 0 | 0 | 0 | 0 | 0 | Sprint zero — squad formation, tooling, environment
S-01 | 2026-07-20 | 2026-07-31 | 45 | 42 | -3 | 5 | 1 | 0 | First delivery sprint
S-02 | 2026-08-03 | 2026-08-14 | 55 | 53 | -2 | 7 | 1 | 1 | Findings: 1 defect on US-AUTH-002
S-03 | 2026-08-17 | 2026-08-28 | 58 | 55 | -3 | 6 | 2 | 0
S-04 | 2026-08-31 | 2026-09-11 | 62 | 0 | -62 | 0 | 0 | 0 | Current — in flight
S-05 | 2026-09-14 | 2026-09-25 | 64 | 0 | -64 | 0 | 0 | 0 | Planned
S-06 | 2026-09-28 | 2026-10-09 | 64 | 0 | -64 | 0 | 0 | 0 | Planned
S-07 | 2026-10-12 | 2026-10-23 | 64 | 0 | -64 | 0 | 0 | 0 | Planned
S-08 | 2026-10-26 | 2026-11-06 | 64 | 0 | -64 | 0 | 0 | 0 | Planned
S-09 | 2026-11-09 | 2026-11-20 | 64 | 0 | -64 | 0 | 0 | 0 | Planned
S-10 | 2026-11-23 | 2026-12-04 | 50 | 0 | -50 | 0 | 0 | 0 | Planned — Thanksgiving short
S-11 | 2026-12-07 | 2026-12-18 | 64 | 0 | -64 | 0 | 0 | 0 | Planned
METRICS
Completed sprints avg velocity: | 50
3-sprint rolling avg: | 50
Avg estimation accuracy (completed/committed): | 94.94%
Total defects escaped to date: | 1
Avg defects per sprint (completed): | 0.33333

## 5. Sprint Retrospectives
Sprint Retrospectives
Keep / Stop / Start items from each sprint retro. Actions carried forward until addressed.
Theme column helps identify systemic patterns — a theme appearing 3+ sprints signals a structural issue.
Sprint | Date | Type | Item | Theme | Action Owner | Status | Notes
S-01 | 2026-07-31 | Keep | Squad-of-4 pair programming for switching safety stories | Safety discipline | Sr Eng C | Ongoing
S-01 | 2026-07-31 | Keep | Daily 10-min 'architecture sync' for Sr Engs only | Coordination | Sr Eng Deputy | Ongoing
S-01 | 2026-07-31 | Stop | Merging PRs without test run on target branch | Quality | All Sr Engs | Closed | CI gate added
S-01 | 2026-07-31 | Start | Documenting AC-to-test mapping in story comments | Traceability | QA Auto 1 | Ongoing
S-02 | 2026-08-14 | Keep | Pair programming for safety-critical continues | Safety discipline | Sr Eng C | Ongoing
S-02 | 2026-08-14 | Stop | Story estimation in squad meetings — move to planning poker async | Estimation | All Sr Engs | Closed | Switched to async poker
S-02 | 2026-08-14 | Start | Weekly BR-code walkthrough for US-AUTH-002 defect root cause | Learning | Sec Eng | Closed | Addressed
S-02 | 2026-08-14 | Keep | 15-min 'intended design' review before coding safety stories | Safety discipline | Sr Eng C | Ongoing
S-03 | 2026-08-28 | Stop | Jr Eng picking up safety-critical stories solo | Safety discipline | Sr Eng C | Closed | Safety = pair programmed always
S-03 | 2026-08-28 | Start | Integration test fixtures shared across squads | Test efficiency | QA Auto 2 | In Progress
S-03 | 2026-08-28 | Keep | Friday afternoon DAB updates to architect-on-call | Architecture discipline | Sr Eng Deputy | Ongoing
S-03 | 2026-08-28 | Start | Tech debt log walkthrough every retro (new practice) | Tech debt management | Sr Eng Deputy | Ongoing | Prevents debt invisibility
S-03 | 2026-08-28 | Stop | Accepting stories without AC-to-test mapping | Quality | POs | Closed | Now in DoR

## 6. Impediment Log
Impediment Log
Anything blocking progress. Escalation path: Sr Eng → PM → Steering (48hr internal / 24hr external cap).
Impediments open >5 business days trigger automatic PM escalation.
ID | Raised Date | Description | Category | Severity | Affected Story/Stories | Owner | Status | Resolved Date | Notes
I-01 | 2026-07-22 | SCADA test environment credentials not rotated; team blocked on US-SCADA-001 | External | High | US-SCADA-001 | Sec Eng | Closed | 2026-07-23 | Resolved <24hr; good
I-02 | 2026-07-30 | Field Work vendor API doc ambiguity on idempotency — blocks US-FWS design | External | Medium | US-FWS-001, US-FWS-002 | Integration Architect | Closed | 2026-08-08 | Vendor clarification + amended INT-02
I-03 | 2026-08-05 | Flyway migration rollback approach unclear for complex migration MIG-06 | Internal | Medium | E-PLT-05 dependent | Data Arch | Closed | 2026-08-12 | Pattern established
I-04 | 2026-08-18 | Integration test env DB performance insufficient for US-SCADA-004 validation | Internal | Medium | US-SCADA-004 | DevOps 1 | Closed | 2026-08-22 | Env rebuilt with SSD
I-05 | 2026-08-26 | GIS vendor unreachable — topology sync validation delayed | External | Medium | US-GIS-001 | Integration Architect | Open |  | Escalated to program manager
I-06 | 2026-09-02 | Security Architect bandwidth constraint — review queue building | Internal | Medium | Multiple | Program Manager | Open |  | Considering secondary reviewer
I-07 | 2026-09-04 | Field Work System test environment differs from prod in auth flow | External | Low | US-FWS-001 | Integration Architect | Open |  | Vendor agreed to align; ETA 2 weeks
I-08 | 2026-09-05 | PM capacity split with cutover planning starting early | Internal | Low | None specific | Program Manager | Open |  | Preparing deputy PM
I-09 | 2026-09-08 | Kafka consumer lag monitoring noise — false alert fatigue | Internal | Low | Observability | DevOps 2 | Open
I-10 | 2026-09-09 | Product Council operator unavailable for US-SWEXEC-001 demo | Internal | Medium | US-SWEXEC-001 | Product Owner | Open |  | Reschedule next week

## 7. Feature Flag Register
Feature Flag Register
Every runtime flag with purpose, owner, and removal criteria. Flags exist for: cutover coordination, incremental rollout, risky changes, kill switches.
Flags with no removal criteria = permanent flags. These need explicit justification.
Flag ID | Flag Name | Purpose | Type | Default | Owner | Created | Removal Criteria / Sunset Date | Status | Notes
F-01 | card.auto-create-enabled | Enable auto-card creation from SCADA events per district | Cutover | false | Ops PO | 2026-07-29 | Remove after full cutover (all districts) | Active | Per-district value
F-02 | card.bulk-open-enabled | Enable bulk card opening during storm declaration | Cutover | false | Ops PO | 2026-08-12 | Remove after full cutover | Active
F-03 | swexec.execute-enabled | Safety gate on switching order execution | Safety kill-switch | false | Ops PO | 2026-09-03 | Permanent — never remove | Permanent | Emergency kill
F-04 | clearance.issue-enabled | Safety gate on clearance issuance | Safety kill-switch | false | Ops PO | 2026-09-03 | Permanent | Permanent | Emergency kill
F-05 | fws.dispatch-enabled | Enable field work dispatch integration per district | Cutover | false | Integration Lead | 2026-08-22 | Remove after full cutover | Active
F-06 | scada.reconciliation-enabled | Enable daily SCADA reconciliation job | Cutover | false | Integration Lead | 2026-09-04 | Enable at pilot cutover | Active
F-07 | ui.new-dashboard-enabled | Rollout of new operator dashboard UI | Rollout | false | UX Lead | 2026-08-28 | Full user migration complete + 2 weeks | Active
F-08 | audit.archival-enabled | Enable cold-storage archival of audit events | Rollout | false | Sec Eng | 2026-09-09 | After production validation | Active
F-09 | reporting.replica-isolated | Use dedicated reporting replica | Cutover | false | DBA | 2026-09-09 | After SP-11 validation | Active
F-10 | storm.degraded-mode-enabled | Auto-shed UI features during extreme load | Safety / resilience | false | Chief Architect | planned | After full cutover + storm validation | Planned | Enable AFTER validating in UAT
F-11 | sw.new-state-machine | New state machine library vs legacy switch-based | Migration | false | Sr Eng C | 2026-09-09 | After SP-06 + validation | Active | ADR-017 rollout
F-12 | observability.fine-grained-tracing | Enable fine-grained tracing (performance cost) | Diagnostic | false | DevOps 2 | 2026-08-20 | Permanent — runtime toggle for incidents | Permanent | Diagnostic tool
F-13 | api.v2-enabled | v2 API available (breaking changes from v1) | Rollout | false | Integration Lead | planned | After all consumers migrated | Planned
F-14 | cutover.legacy-read-only | Put legacy system in read-only mode | Cutover | false | Program Manager | planned | Per-district: activated at cutover; removed at hypercare exit | Planned | Coordinated with legacy ops
F-15 | mvp.non-mvp-features-hidden | Hide non-MVP features from UI until ready | Rollout | true | UX Lead | 2026-08-01 | As each non-MVP feature ships | Active

## 8. Tech Debt Register
Tech Debt Register
Deliberate deferrals tracked and prioritized. Target: debt ratio <= 15% of points/sprint.
Every debt item links to why it was incurred and paydown plan. Safety-critical debt has 30-day resolution cap.
Debt ID | Description | Category | Severity | Origin Sprint | Linked Story | Effort (pts) | Priority | Target Sprint | Status | Notes
TD-01 | Temp in-memory dedup cache (US-SCADA-002) — move to Redis for HA | Architecture | High | S-02 | US-SCADA-002 | 5 | H | S-07 | Open | ADR-004 proper implementation
TD-02 | Shared test fixtures scattered across squad repos | Testing | Medium | S-01 | multiple | 5 | M | S-06 | In Progress | Retro action S-03
TD-02b | Audit event envelope versioning deferred to v2 | Design | Low | S-01 | US-AUDIT-002 | 3 | L | S-12 | Open | Not limiting now
TD-03 | Switching step precondition library — hardcoded vs data-driven | Architecture | High | S-04 | US-SWEXEC-002 | 8 | H | S-09 | Open | Technical ceiling approaching; SP-09 outcome
TD-04 | UI component library drift across Ops Core and Switching squads | UI | Medium | S-02 | multiple | 8 | M | S-08 | Open | FE tech lead addressing
TD-05 | Integration test env data refresh manual — should be automated | Tooling | Medium | S-01 | N/A | 5 | M | S-08 | Open | DevOps queue
TD-06 | FW System dispatch: first implementation skipped idempotency key in body | Integration | High | S-05 | US-FWS-001 | 3 | H | S-06 | Open | Pay down before cutover
TD-07 | Log levels inconsistent across squads | Observability | Low | S-03 | multiple | 3 | L | S-10 | Open | Standards doc needed
TD-08 | Defect US-AUTH-002 root cause: missing test scenario for district cross-scope | Test coverage | High | S-02 | US-AUTH-002 | 5 | H | S-05 | Closed | Addressed
TD-09 | Kafka consumer offset commit pattern manual — should use auto-commit with care | Integration | Medium | S-02 | US-SCADA-001 | 3 | M | S-09 | Open
TD-10 | DB connection pool sizing not load-tested | Platform | Medium | S-03 | N/A | 3 | M | S-09 | Open | Spike planned
TD-11 | Feature flag evaluation hot path allocates on every call | Performance | Low | S-04 | all flagged stories | 2 | L | S-12 | Open
TD-12 | No circuit breaker on CIS integration calls | Resilience | Medium | S-04 | US-CIS-001 planned | 5 | M | S-08 | Open | Will be issue at storm load
TD-13 | Migration reconciliation scripts one-off — generalize | Migration | Medium | S-03 | E-PLT-05 | 5 | M | S-10 | Open | Data Arch
TD-14 | Safety-critical: grounding rule check bypass code path possible via race condition | SAFETY | CRITICAL | S-04 | US-SWEXEC-002 | 8 | CRITICAL | S-05 | Open | 30-day cap — must resolve
TD-15 | Retrospective action tracking manual | Process | Low | S-03 | N/A | 2 | L | S-11 | Open | Non-urgent
SUMMARY
Total debt items: | -252
CRITICAL open: | 1
High open: | 3
Total open points: | 63
Safety debt items: | 1

## 9. Code Review Findings
Code Review Findings — Systemic Patterns
Not individual code review comments (those stay in PR). This tab captures SYSTEMIC patterns spotted across reviews that need team-level attention.
Findings drive retro actions, documentation updates, training, or automated lint rules.
Finding ID | Pattern | Category | Occurrences (approx) | First Seen Sprint | Severity | Owner | Remediation Plan | Status
CR-01 | Using Optional.get() without isPresent() check | Quality | 8 | S-01 | Medium | Sr Eng Deputy | Added Checkstyle rule; squad-level training in S-03 | Closed
CR-02 | Audit events missing correlation ID when emitted from async contexts | Safety | 4 | S-02 | High | Sr Eng Deputy | Audit library refactor; correlation context propagation (US-AUDIT-005) | In Progress
CR-03 | Safety-critical precondition checks in conditionals rather than explicit | Safety | 3 | S-03 | High | Sr Eng C | Established precondition evaluator pattern; refactoring sweep | In Progress
CR-04 | Kafka consumer error handling swallows exceptions silently | Resilience | 2 | S-02 | High | Sr Eng A | Standard error handler; topic-specific DLQ | Closed
CR-05 | SQL constructed via string concatenation in a few places | Security | 2 | S-02 | High | Sec Eng | Linted; found-and-fixed; added to pre-commit | Closed
CR-06 | UI components not handling loading/error/empty states consistently | UI | 12 | S-02 | Medium | FE Tech Lead | Component library templates; Storybook checks | In Progress
CR-07 | Integration retries missing jitter (thundering herd risk) | Resilience | 3 | S-03 | Medium | Sr Eng A | Standard retry utility; refactor sweep | Closed
CR-08 | Tests using production-like data volume slow CI | Testing | 5 | S-03 | Low | QA Auto 1 | Test data minimization; fixture sharing | In Progress
CR-09 | Controller methods doing too much — thin-controller guideline not followed | Architecture | 6 | S-02 | Medium | Sr Eng Deputy | Code review checklist emphasis; refactoring examples | Ongoing
CR-10 | Missing district-scope guards on some queries | Security/Safety | 2 | S-03 | High | Sec Eng + Sr Eng Deputy | Audit via code-scan; standard repository base class | In Progress
CR-11 | Logs containing customer identifiers (PII leakage risk) | Security | 3 | S-03 | High | Sec Eng | Log sanitization library; pre-commit scan | Closed
CR-12 | State machine transitions via enum switch rather than explicit machine | Legacy pattern | 4 | S-03 | Medium | Chief Architect | Migrate to state machine library (linked to ADR-017); refactor plan | In Progress

## 10. Build Phase Risks
Build Phase Risk Log
Risks specific to Build phase. Reviewed every 2 sprints by Program Manager + Sr Engs.
CRITICAL or HIGH open risks >4 weeks trigger steering escalation.
Risk ID | Description | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status | Notes
BR-01 | Sprint velocity below committed 4+ sprints running | 3 | 4 | 12 | 3-sprint rolling average tracked; commitment capped at rolling avg * 0.9 | Program Manager | Active
BR-02 | Safety-critical defect escapes to test or UAT | 3 | 5 | 15 | Pair programming; dual code review; Product Council demo before accept; test coverage gates | Sr Eng C | Active
BR-03 | Technical debt accumulates faster than paid down | 4 | 3 | 12 | 15% debt ratio cap; retro walks through debt register; paydown sprints if breached | Sr Eng Deputy | Active | Monitored
BR-04 | Integration with Field Work System blocks entire sprint | 3 | 4 | 12 | Mock/stub for test env; vendor escalation path; alternative batch path designed (TD) | Integration Lead | Active
BR-05 | Key-person dependency on Chief Architect for unblocking | 4 | 4 | 16 | Sr Eng Deputy takes 50% of routine reviews; DAB decisions batched; ADR library mature | Sr Eng Deputy | Active
BR-06 | Mid-engineers ramp slower than planned | 3 | 3 | 9 | Pairing rotation; dedicated mentoring time in capacity; knowledge-share sessions | Sr Engs | Active
BR-07 | Jr engineers taking on too much risk | 2 | 3 | 6 | Safety-critical stories exclude Jr solo; explicit DoR check for story match to engineer | Sr Engs | Active
BR-08 | Test env instability reduces team throughput | 3 | 3 | 9 | DevOps dedicated env maintenance allocation; env health dashboard | DevOps 1 | Active
BR-09 | Requirement changes arriving mid-sprint (scope creep) | 3 | 3 | 9 | Change control process; POs gate in-sprint changes; retro signals | POs + PM | Active
BR-10 | Product Council availability during peak storm periods | 3 | 3 | 9 | Scheduled well in advance; backup operator roster per area; async review for non-demos | Program Manager | Active
BR-11 | Non-MVP feature creeping into MVP | 3 | 4 | 12 | Quarterly MVP scope review with steering; PO discipline; feature flags to defer | POs | Active
BR-12 | Data migration dress rehearsals reveal unresolvable issues | 2 | 4 | 8 | Start rehearsals early in Phase 3; fallback approaches documented for each migration | Data Migration Lead | Active
BR-13 | Storm in region during Build — team impact | 3 | 3 | 9 | Identified backup resources; prioritize finish-current-sprint over starting new | Program Manager | Active
BR-14 | NERC CIP compliance artifacts lag build | 3 | 4 | 12 | Compliance Officer sprint-0 engagement; evidence generation automated where possible | Sec Eng | Active
BR-15 | Tool/license change mid-Build forces rework | 2 | 3 | 6 | Tech debt register includes vendor/license trajectory watchpoints; contingency buffers | Chief Architect | Active

## 11. Build Dashboard
Build Dashboard — KPI Roll-up
Pulls metrics from other tabs. Refreshed weekly by Program Manager. Reviewed in steering monthly.
Thresholds: green within target; amber = watchlist; red = action needed.
Metric | Value | Target | Notes
DELIVERY
DELIVERY
Velocity (3-sprint rolling avg) | 0 | 60 | Rolling average of completed points
Estimation accuracy | 0 | >85% | Completed / committed
Total story points completed to date | 300 | — | Cumulative
% MVP complete (by points) | 4 | Tracking
QUALITY
Defects escaped (cumulative) | 0 | <5
Defects per sprint (avg completed) | 0 | <2
Code review findings Open (High/CRITICAL) | 3 | <=5 | Systemic patterns
HEALTH
Open impediments | 6 | <8 | Active blockers
Escalated impediments | 0 | 0
Tech debt open points | 63 | <=30 | <=15% of 3-sprint rolling velocity
Tech debt CRITICAL items open | 1 | 0 | 30-day cap per CRITICAL
Safety debt items open | 1 | 0 | All must be addressed
RISK
Build risks active (score >=15) | 2 | <=2
Build risks active (score 8-14) | 11 | <=5
FEATURE FLAGS
Active flags | 9 | —
Permanent flags (justified) | 3 | —